## Summary
VMware exit - wave 1 - V2V - Virtual to Virtual: VMware vSphere / ESXi (vCenter) to Nutanix AHV (Prism)
Measure | Value
Scenario | V2V - Virtual to Virtual: VMware vSphere / ESXi (vCenter) to Nutanix AHV (Prism)
Recommended tool | Commvault Cloud (Complete Backup & Recovery)
OEM / vendor | Commvault
Cost posture | Paid - Per-TB front-end or per-VM subscription
Cutover profile | Warm - seeded online, short cutover window
Workloads in scope | 180
Data to move | 46.0 TB
Link between source and target | 1,000 Mbps
Raw transfer time at 65% efficiency | 6.9 days
Realistic elapsed time | 11 days allowing for delta passes, retries and contention
Waves | 9 waves of about 20

## Requirements
Question | Answer
Project | VMware exit - wave 1
Organisation | Niyyasoft
Migration type | V2V - Virtual to Virtual
Source platform | VMware vSphere / ESXi (vCenter)
Target platform | Nutanix AHV (Prism)
Workloads in scope | 180
Data volume | 46.0 TB
Available bandwidth | 1,000 Mbps
Guest operating systems | Windows, Linux
Downtime tolerance | A planned maintenance window
Budget posture | Cost is secondary to capability
Required capabilities | Changed-block tracking / incremental sync; Live migration (no guest downtime); Non-disruptive test migration; Rollback / failback after cutover; Agentless operation; Discovery and assessment; Application dependency mapping; Programme reporting / audit trail
Regulated / audit evidence needed | No

## Shortlist
Rank | Tool | OEM / vendor | Cost | Licensing model | Cutover profile | Deployment | Scale | Lifecycle | Fit score | Why it fits | Watch out for
1 | Commvault Cloud (Complete Backup & Recovery) | Commvault | Paid | Per-TB front-end or per-VM subscription | Warm - seeded online, short cutover window | Both | Enterprise | Current | 150 | Supports V2V as a first-class scenario. Explicitly supports VMware vSphere / ESXi (vCenter) as a source and Nutanix AHV (Prism) as a target. Wave and batch orchestration, which matters at 180 workloads. Agentless, so there is no per-server software deployment to get approved. Provides changed-block tracking / incremental sync. Provides non-disruptive test migration. Provides agentless operation. Provides discovery and assessment. Provides programme reporting / audit trail. | Does not provide live migration (no guest downtime). Does not provide rollback / failback after cutover. Does not provide application dependency mapping.
2 | Veeam Data Platform (Backup & Replication) | Veeam Software | Paid | Veeam Universal Licence (VUL), typically sold in 10-instance packs | Warm - seeded online, short cutover window | Both | Enterprise | Current | 150 | Supports V2V as a first-class scenario. Explicitly supports VMware vSphere / ESXi (vCenter) as a source and Nutanix AHV (Prism) as a target. Wave and batch orchestration, which matters at 180 workloads. Agentless, so there is no per-server software deployment to get approved. Provides changed-block tracking / incremental sync. Provides non-disruptive test migration. Provides rollback / failback after cutover. Provides agentless operation. Provides programme reporting / audit trail. | Does not provide live migration (no guest downtime). Does not provide discovery and assessment. Does not provide application dependency mapping.
3 | Nutanix Move | Nutanix | Included | No charge to Nutanix customers | Warm - seeded online, short cutover window | Agentless | Enterprise | Current | 138 | Supports V2V as a first-class scenario. Explicitly supports VMware vSphere / ESXi (vCenter) as a source and Nutanix AHV (Prism) as a target. Purpose-built for Nutanix AHV (Prism) - this is the platform-native migration path. Wave and batch orchestration, which matters at 180 workloads. Agentless, so there is no per-server software deployment to get approved. Provides changed-block tracking / incremental sync. Provides non-disruptive test migration. Provides agentless operation. | Does not provide live migration (no guest downtime). Does not provide rollback / failback after cutover. Does not provide discovery and assessment. Does not provide application dependency mapping. Does not provide programme reporting / audit trail.
4 | NAKIVO Backup & Replication | NAKIVO | Paid | Per-socket or per-workload perpetual/subscription; free trial and a free edition for small use | Warm - seeded online, short cutover window | Both | Mid | Current | 134 | Supports V2V as a first-class scenario. Explicitly supports VMware vSphere / ESXi (vCenter) as a source and Nutanix AHV (Prism) as a target. Built specifically for a small set of targets including Nutanix AHV (Prism), rather than reaching it as a generalist. Wave and batch orchestration, which matters at 180 workloads. Agentless, so there is no per-server software deployment to get approved. Provides changed-block tracking / incremental sync. Provides rollback / failback after cutover. Provides agentless operation. | Does not provide live migration (no guest downtime). Does not provide non-disruptive test migration. Does not provide discovery and assessment. Does not provide application dependency mapping. Does not provide programme reporting / audit trail.
5 | Cohesity DataProtect (incl. Veritas NetBackup) | Cohesity | Paid | Per-TB or per-workload subscription | Warm - seeded online, short cutover window | Both | Enterprise | Current | 126 | Supports V2V as a first-class scenario. Explicitly supports VMware vSphere / ESXi (vCenter) as a source and Nutanix AHV (Prism) as a target. Wave and batch orchestration, which matters at 180 workloads. Agentless, so there is no per-server software deployment to get approved. Provides changed-block tracking / incremental sync. Provides agentless operation. Provides programme reporting / audit trail. | Does not provide live migration (no guest downtime). Does not provide non-disruptive test migration. Does not provide rollback / failback after cutover. Does not provide discovery and assessment. Does not provide application dependency mapping.
6 | Rubrik Security Cloud | Rubrik | Paid | Per-TB subscription | Warm - seeded online, short cutover window | Both | Enterprise | Current | 122 | Supports V2V as a first-class scenario. Explicitly supports VMware vSphere / ESXi (vCenter) as a source and Nutanix AHV (Prism) as a target. Built specifically for a small set of targets including Nutanix AHV (Prism), rather than reaching it as a generalist. Wave and batch orchestration, which matters at 180 workloads. Agentless, so there is no per-server software deployment to get approved. Provides changed-block tracking / incremental sync. Provides agentless operation. | Does not provide live migration (no guest downtime). Does not provide non-disruptive test migration. Does not provide rollback / failback after cutover. Does not provide discovery and assessment. Does not provide application dependency mapping. Does not provide programme reporting / audit trail.
7 | Storware Backup & Recovery (vProtect) | Storware | Paid | Per-VM or per-socket subscription | Warm - seeded online, short cutover window | Agentless | Mid | Current | 114 | Supports V2V as a first-class scenario. Explicitly supports VMware vSphere / ESXi (vCenter) as a source and Nutanix AHV (Prism) as a target. Wave and batch orchestration, which matters at 180 workloads. Agentless, so there is no per-server software deployment to get approved. Provides changed-block tracking / incremental sync. Provides agentless operation. | Does not provide live migration (no guest downtime). Does not provide non-disruptive test migration. Does not provide rollback / failback after cutover. Does not provide discovery and assessment. Does not provide application dependency mapping. Does not provide programme reporting / audit trail.
8 | Vinchin Backup & Recovery | Vinchin | Paid | Per-socket / per-host perpetual or subscription; 60-day full-feature trial | Warm - seeded online, short cutover window | Both | Mid | Current | 110 | Supports V2V as a first-class scenario. Explicitly supports VMware vSphere / ESXi (vCenter) as a source and Nutanix AHV (Prism) as a target. Wave and batch orchestration, which matters at 180 workloads. Agentless, so there is no per-server software deployment to get approved. Provides changed-block tracking / incremental sync. Provides agentless operation. | Does not provide live migration (no guest downtime). Does not provide non-disruptive test migration. Does not provide rollback / failback after cutover. Does not provide discovery and assessment. Does not provide application dependency mapping. Does not provide programme reporting / audit trail.
9 | VMware OVF Tool / OVA export-import | Broadcom (VMware) | Free | No licence cost | Cold - full outage for the whole copy | Agentless | Smb | Current | 22 | Supports V2V as a first-class scenario. Explicitly supports VMware vSphere / ESXi (vCenter) as a source and Nutanix AHV (Prism) as a target. | Cutover profile is "Cold - full outage for the whole copy", which is weaker than the downtime you asked for. Designed for smaller estates than 180 workloads - expect manual effort or many batches. Does not provide changed-block tracking / incremental sync. Does not provide live migration (no guest downtime). Does not provide non-disruptive test migration. Does not provide rollback / failback after cutover. Does not provide agentless operation. Does not provide discovery and assessment. Does not provide application dependency mapping. Does not provide programme reporting / audit trail.
10 | qemu-img | QEMU project | Open source | No licence cost (GPL) | Cold - full outage for the whole copy | Agentless | Smb | Current | 14 | Supports V2V as a first-class scenario. | Cutover profile is "Cold - full outage for the whole copy", which is weaker than the downtime you asked for. Designed for smaller estates than 180 workloads - expect manual effort or many batches. Does not provide changed-block tracking / incremental sync. Does not provide live migration (no guest downtime). Does not provide non-disruptive test migration. Does not provide rollback / failback after cutover. Does not provide agentless operation. Does not provide discovery and assessment. Does not provide application dependency mapping. Does not provide programme reporting / audit trail.

## Licensing
Tool | OEM / vendor | Cost | Indicative price | Licence model | How to license it | Reference
Commvault Cloud (Complete Backup & Recovery) | Commvault | Paid | Per-TB front-end or per-VM subscription | Subscription by front-end terabyte or per-VM/per-instance, depending on the package. | Quote through Commvault or a partner; also on AWS/Azure marketplaces for cloud-spend drawdown. | https://www.commvault.com/
Veeam Data Platform (Backup & Replication) | Veeam Software | Paid | Veeam Universal Licence (VUL), typically sold in 10-instance packs | Veeam Universal Licence - portable instances that can be applied to VMs, physical servers, cloud instances or workstations. Per-socket perpetual licences still exist for legacy estates but VUL is the current model. | Buy VUL instance packs (annual subscription, 1/3/5 year) from Veeam or a ProPartner, or via the AWS/Azure marketplace. A licence file is uploaded to the Veeam console. Veeam Community Edition is free for up to 10 instances and can do cross-platform Instant Recovery - enough for a small migration. | https://www.veeam.com/products/veeam-data-platform.html
Nutanix Move | Nutanix | Included | No charge to Nutanix customers | Free downloadable appliance for any customer with a Nutanix cluster under support. | Sign in to the Nutanix Support Portal with your cluster entitlement and download the Move appliance (OVA/QCOW2). No licence key. Support is covered by your existing AOS contract. | https://www.nutanix.com/products/move
NAKIVO Backup & Replication | NAKIVO | Paid | Per-socket or per-workload perpetual/subscription; free trial and a free edition for small use | Perpetual per-socket (hypervisor hosts) or per-workload subscription. NAKIVO also offers a limited free edition. | Buy from NAKIVO or a reseller and apply the licence in the Director web console. Sizing is per CPU socket on the source hosts or per protected workload. | https://www.nakivo.com/
Cohesity DataProtect (incl. Veritas NetBackup) | Cohesity | Paid | Per-TB or per-workload subscription | Capacity or workload-based subscription. | Quote through Cohesity or a partner. | https://www.cohesity.com/
Rubrik Security Cloud | Rubrik | Paid | Per-TB subscription | Capacity-based subscription. | Quote through Rubrik or a partner. | https://www.rubrik.com/
Device42 (Freshworks) | Freshworks (Device42) | Paid | Annual subscription by device count | Annual subscription sized on managed devices. | Quote from Device42/Freshworks or a partner; free trial available. | https://www.device42.com/
Faddom | Faddom | Paid | Subscription by server count; free tier for small estates | Subscription by number of servers; a free tier covers small environments. | Self-service sign-up with a free tier, then upgrade by server count. | https://faddom.com/
Flexera One (Cloud Migration & Optimization) | Flexera | Paid | Enterprise subscription, quote based | Enterprise SaaS subscription. | Quote from Flexera. | https://www.flexera.com/
Google Cloud Migration Center | Google Cloud | Free | No charge | Free Google Cloud service. | Enable the API in your project. No cost. | https://cloud.google.com/migration-center

## Plan
Phase | Phase objective | Activity | Owner | Start | Finish
Discover | Inventory the estate, profile performance, map application dependencies and agree the scope. | Run an inventory export (RVTools for vSphere, PowerShell for Hyper-V) and reconcile it against the CMDB.
Discover | Inventory the estate, profile performance, map application dependencies and agree the scope. | Profile 7 days of CPU, memory, IOPS and network so the target is sized on real load, not on allocation.
Discover | Inventory the estate, profile performance, map application dependencies and agree the scope. | Map application dependencies and agree the move groups - anything that talks to anything else moves in the same wave.
Discover | Inventory the estate, profile performance, map application dependencies and agree the scope. | Flag workloads that cannot be migrated as-is: licence-locked appliances, USB dongles, physical HBAs, unsupported OS versions.
Design | Size and build the target platform, design networking and storage, pick the tool and prove it in a PoC. | Size and build the target Nutanix AHV (Prism) capacity including N+1.
Design | Size and build the target platform, design networking and storage, pick the tool and prove it in a PoC. | Design IP addressing: keep the same subnets (stretched or re-created) or plan the re-addressing and DNS changes per wave.
Design | Size and build the target platform, design networking and storage, pick the tool and prove it in a PoC. | Confirm backup, monitoring, antivirus and patching agents exist for the target platform.
Design | Size and build the target platform, design networking and storage, pick the tool and prove it in a PoC. | Prove Commvault Cloud (Complete Backup & Recovery) in a proof of concept against one real workload from each application family.
Prepare | Deploy migration infrastructure, open firewall paths, stage agents, build move groups and waves. | Deploy the Commvault Cloud (Complete Backup & Recovery) infrastructure and open the required firewall paths.
Prepare | Deploy migration infrastructure, open firewall paths, stage agents, build move groups and waves. | Stage guest tools / VirtIO / cloud agents on source VMs ahead of cutover where the tool does not inject them.
Prepare | Deploy migration infrastructure, open firewall paths, stage agents, build move groups and waves. | Build the wave plan and book the change windows with each application owner.
Prepare | Deploy migration infrastructure, open firewall paths, stage agents, build move groups and waves. | Agree and document the rollback trigger and the decision owner for each wave.
Pilot | Migrate a low-risk wave end to end, measure throughput, validate the runbook and fix what broke. | Migrate one low-risk, non-production wave end to end.
Pilot | Migrate a low-risk wave end to end, measure throughput, validate the runbook and fix what broke. | Measure actual throughput and extrapolate the real programme duration.
Pilot | Migrate a low-risk wave end to end, measure throughput, validate the runbook and fix what broke. | Run the full validation script and capture how long cutover really takes.
Pilot | Migrate a low-risk wave end to end, measure throughput, validate the runbook and fix what broke. | Update the runbook with what broke - there will be something.
Migrate | Run production waves on the agreed cadence with seeded replication and short cutover windows. | Seed replication for the next wave while the current wave is being validated.
Migrate | Run production waves on the agreed cadence with seeded replication and short cutover windows. | Hold a go/no-go 24 hours before each cutover.
Migrate | Run production waves on the agreed cadence with seeded replication and short cutover windows. | Keep a daily burn-down of migrated versus remaining workloads.
Migrate | Run production waves on the agreed cadence with seeded replication and short cutover windows. | Re-baseline throughput weekly; bandwidth contention is the usual cause of slippage.
Cutover | Final delta sync, stop the source, repoint DNS/load balancers, power on in the target, smoke test. | Final delta sync, then quiesce and shut down the source guest.
Cutover | Final delta sync, stop the source, repoint DNS/load balancers, power on in the target, smoke test. | Power on in the target, verify IP, DNS, domain membership and time sync.
Cutover | Final delta sync, stop the source, repoint DNS/load balancers, power on in the target, smoke test. | Remove source-platform tools and install target-platform tools/drivers.
Cutover | Final delta sync, stop the source, repoint DNS/load balancers, power on in the target, smoke test. | Run the application smoke test and get the owner to sign the checklist.
Validate | Application and business sign-off, performance comparison, backup and monitoring re-onboarding. | Compare performance against the pre-migration baseline and resize where needed.
Validate | Application and business sign-off, performance comparison, backup and monitoring re-onboarding. | Re-onboard to backup and monitoring, and prove one restore.
Validate | Application and business sign-off, performance comparison, backup and monitoring re-onboarding. | Confirm licensing is correct on the new platform - core counts and socket counts change.
Validate | Application and business sign-off, performance comparison, backup and monitoring re-onboarding. | Formal business sign-off per application.
Decommission | Hold the source in a recoverable state for the agreed period, then reclaim licences and hardware. | Keep the source VM powered off but intact for the agreed hold period (30 days is typical).
Decommission | Hold the source in a recoverable state for the agreed period, then reclaim licences and hardware. | Delete migration agents, appliances and temporary firewall rules.
Decommission | Hold the source in a recoverable state for the agreed period, then reclaim licences and hardware. | Reclaim source licences and update the CMDB and DR documentation.
Decommission | Hold the source in a recoverable state for the agreed period, then reclaim licences and hardware. | Close out the wave in the programme record.

## Prerequisites
Prerequisite | Detail | Owner | Status
Management access | Administrative credentials on the source platform (VMware vSphere / ESXi (vCenter)) and the target (Nutanix AHV (Prism)).
Migration network | Routed path from the migration appliance/agents to both platforms, with the replication ports open and no deep packet inspection in the way.
Common ports | TCP 443 (platform APIs and most replication), TCP 902 (ESXi NFC), TCP 22 (Linux/appliance), TCP 445/135 + dynamic RPC (Windows agent push), TCP 1500-1520 (replication varies by product).
Name resolution and time | Forward and reverse DNS for every host involved, and NTP consistency - clock skew breaks certificate and Kerberos-based agents.
Staging capacity | Free capacity on the target for the full wave plus snapshots, typically 1.3x the source footprint during the run.
Guest preparation | Local admin/root on each guest, a current backup taken immediately before cutover, and target platform drivers staged.
Change control | Approved change windows per wave and a named rollback owner.
Licensing for Commvault Cloud (Complete Backup & Recovery) | Quote through Commvault or a partner; also on AWS/Azure marketplaces for cloud-spend drawdown.

## Risks
Risk | Impact | Mitigation | Owner | Status
Guest drivers or boot configuration break on the target platform | High | Stage target drivers (VirtIO, Hyper-V IC, cloud agents) before cutover and test one guest per OS family in the pilot.
Software licensing changes on the new platform | High | Review Oracle, SQL Server, SAP and Windows Server licence terms against the target core/socket model before committing - this can dwarf the migration cost.
IP re-addressing breaks hardcoded dependencies | Medium | Prefer L2 extension or identical subnets; where re-addressing is unavoidable, scan configuration files and firewall rules for literal IPs first.
Backup and monitoring coverage lapses after cutover | Medium | Make backup onboarding and a proven restore part of the wave exit criteria.
Discovery is incomplete and workloads appear late | High | Reconcile at least two independent inventory sources and freeze scope with a dated baseline.
Bandwidth is shared with production and throughput collapses | High | Measure real throughput in the pilot, rate-limit replication during business hours, and re-plan waves on actual numbers.
No agreed rollback trigger, so a bad cutover drags on | High | Define the rollback decision point, the owner and the time limit for every wave before it starts.
Application owners are not engaged and sign-off stalls | Medium | Name an accountable owner and a test script per application during Discover, not during Cutover.

## Waves
Wave | Population | Target size | Planned date | Cutover window | Owner | Status
Wave 1 | IT / internal | 20 |  |  |  | Not started
Wave 2 | Friendly business unit | 20 |  |  |  | Not started
Wave 3 | Business unit 2 | 20 |  |  |  | Not started
Wave 4 | Business unit 3 | 20 |  |  |  | Not started
Wave 5 | Business unit 4 | 20 |  |  |  | Not started
Wave 6 | Business unit 5 | 20 |  |  |  | Not started
Wave 7 | Business unit 6 | 20 |  |  |  | Not started
Wave 8 | Business unit 7 | 20 |  |  |  | Not started
Wave 9 | Business unit 8 | 20 |  |  |  | Not started

## Tool catalogue
Tool | OEM / vendor | Domain | Types | Cost | Indicative price | Licence model | How to license it | Cutover profile | Deployment | Scale | Lifecycle | Capabilities | Strengths | Limitations | Reference
VMware vCenter Converter Standalone | Broadcom (VMware) | workload | P2V, V2V | Free | No licence cost | Free-of-charge standalone download; no licence key required. | Create a free Broadcom Support Portal account, then download Converter Standalone (6.6.x) from the VMware free-downloads section. No entitlement or contract needed. Support is community-only. | Warm - seeded online, short cutover window | Agent | Smb | Legacy | Automatic driver / guest tools injection; Non-disruptive test migration | The classic hot-clone P2V tool. Simple wizard, converts a running Windows server into a vSphere VM with no extra infrastructure. | Windows guests only in 6.x (Linux conversion was dropped), no changed-block tracking, single-job focus, slow over WAN, and long gaps between releases. Not suitable for large waves. | https://knowledge.broadcom.com/external/article/326316
VMware HCX (Hybrid Cloud Extension) | Broadcom (VMware) | workload | V2V, V2C, C2V, C2C | Included | Included with VCF / cloud SDDC; Enterprise tier is an add-on | HCX Advanced is entitled through VMware Cloud Foundation (VCF) and is included at no extra charge with AVS, VMware Cloud on AWS, GCVE and OCVS. HCX Enterprise (Replication Assisted vMotion, OS Assisted Migration, mobility groups) is a paid add-on. | If you are migrating INTO a cloud SDDC, HCX Advanced comes with the SDDC subscription - activate it from the cloud console and it issues the on-prem activation key. For on-prem to on-prem, you need VCF entitlement from Broadcom; HCX Enterprise is ordered per CPU/core through Broadcom or a partner. | Live - no guest downtime | Agentless | Enterprise | Current | Live migration (no guest downtime); Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; Network and IP mapping; Encryption in flight; Non-disruptive test migration; API / CLI automation | The reference tool for large vSphere estates. Layer-2 network extension means IP addresses survive the move, bulk migration handles hundreds of VMs per wave, and vMotion-class cutover gives zero downtime. | Heavy appliance footprint on both ends, vSphere-to-vSphere only, and the on-prem-to-on-prem use case now depends on a VCF subscription. | https://www.vmware.com/products/cloud-infrastructure/hcx
Advanced Cross vCenter vMotion (XVM) | Broadcom (VMware) | workload | V2V | Included | Included with vSphere Enterprise Plus / VCF | Native vCenter feature. Requires vSphere Enterprise Plus (or VVF/VCF) on both source and destination for vMotion; cold relocate works on lower editions. | No separate SKU. Ensure both vCenters carry Enterprise Plus / VVF / VCF keys in Broadcom Support Portal. | Live - no guest downtime | Agentless | Large | Current | Live migration (no guest downtime); Agentless operation; Wave / batch orchestration; API / CLI automation | Built into vCenter 7 U1+. Moves VMs between vCenters in different SSO domains with no shared storage and no extra appliance. | vSphere only, needs good latency/bandwidth between sites, no L2 extension so IP re-addressing must be planned. | https://docs.vmware.com/
vSphere Replication | Broadcom (VMware) | workload | V2V | Included | Included from vSphere Essentials Plus upwards | Bundled entitlement with vSphere Essentials Plus and above (and with VMware Live Recovery / SRM). | Download the vSphere Replication appliance under your existing vSphere entitlement in Broadcom Support Portal. No separate key. | Warm - seeded online, short cutover window | Agentless | Mid | Current | Changed-block tracking / incremental sync; Agentless operation; Rollback / failback after cutover | Free with vSphere, per-VM RPO from 5 minutes, good for moving a few dozen VMs between clusters or sites. | No orchestration or network mapping without SRM; manual power-on at the target. | https://www.vmware.com/products/
VMware Live Recovery (Site Recovery Manager) | Broadcom (VMware) | workload | V2V, V2C | Paid | Subscription, licensed per protected VM | Subscription per protected virtual machine (formerly SRM per-VM packs of 25). | Order through Broadcom or a Broadcom Advantage partner as a term subscription sized on protected VM count. Existing perpetual SRM keys carry over until renewal. | Near-zero - continuous sync, minutes to cut over | Agentless | Enterprise | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Non-disruptive test migration; Rollback / failback after cutover; Network and IP mapping; API / CLI automation; Agentless operation | Recovery-plan orchestration with non-disruptive test failover - ideal when migration must be rehearsed and signed off before cutover. | Priced for DR, not one-off migration; vSphere-centric. | https://www.vmware.com/products/cloud-infrastructure/live-recovery
VMware OVF Tool / OVA export-import | Broadcom (VMware) | workload | V2V | Free | No licence cost | Free developer tool download. | Download from the Broadcom developer portal with a free account. No key. | Cold - full outage for the whole copy | Agentless | Smb | Current | API / CLI automation | Scriptable CLI export/import in the open OVF/OVA format - the universal escape hatch that almost every hypervisor can read. | Cold only, one VM at a time, and large OVAs are slow. Guest drivers still have to be fixed after import. | https://developer.broadcom.com/tools/open-virtualization-format-ovf-tool/latest
Azure Migrate (Discovery, Assessment & Server Migration) | Microsoft | workload, assessment | V2C, P2C, C2C | Free | Tool is free; first 180 days of replication per server included | Azure Migrate itself carries no licence fee. Discovery and assessment are free. Server migration is free for the first 180 days per machine, after which Azure Site Recovery per-instance charges apply. You still pay for the target Azure compute, storage and network. | Create an Azure Migrate project in any Azure subscription - no SKU to buy. Deploy the Azure Migrate appliance OVA/VHD on-prem. Use Azure Hybrid Benefit to carry existing Windows Server / SQL Server licences into Azure. | Near-zero - continuous sync, minutes to cut over | Both | Enterprise | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; Discovery and assessment; Application dependency mapping; Non-disruptive test migration; Encryption in flight; API / CLI automation; Programme reporting / audit trail | One console for inventory, dependency mapping, right-sizing, TCO modelling and the actual replication. Agentless for VMware and Hyper-V. Free for the migration window itself. | Azure only. Agentless VMware replication has disk-count and size limits; very large or very chatty servers may need the agent-based path. | https://learn.microsoft.com/azure/migrate/
Azure Site Recovery (ASR) | Microsoft | workload | V2C, P2C, C2C, V2V | Paid | First 31 days free per instance, then roughly US$16-25 per protected instance per month | Consumption-based Azure meter per protected instance per month, plus storage, snapshots and egress. Azure-to-Azure and on-prem-to-Azure are metered separately. | No purchase order - it bills straight to your Azure subscription. Use a Recovery Services vault. The 31-day free period per new instance covers most migration cutovers at zero replication cost. | Near-zero - continuous sync, minutes to cut over | Both | Enterprise | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Non-disruptive test migration; Rollback / failback after cutover; Network and IP mapping; Encryption in flight; API / CLI automation | Continuous replication with test failover into an isolated Azure vNet - you can rehearse cutover as often as you like before committing. | The classic VMware/physical-to-Azure path is being folded into Azure Migrate. Check the current supported-scenario matrix before designing around it. | https://azure.microsoft.com/products/site-recovery
Disk2vhd (Sysinternals) | Microsoft | workload | P2V | Free | No licence cost | Free Sysinternals utility under the Sysinternals licence terms. | Download from Microsoft Learn or run it straight from \\live.sysinternals.com\tools. No key, no registration. | Warm - seeded online, short cutover window | Agent | Smb | Current |  | Tiny single executable that snapshots a live Windows machine to VHD/VHDX using VSS. The pragmatic answer for a handful of stragglers, and the VHDX converts on to almost any platform. | Windows only, no incremental sync, no orchestration, and the resulting VHDX has to be moved and fixed up by hand. Do not use it for domain controllers. | https://learn.microsoft.com/sysinternals/downloads/disk2vhd
Microsoft Virtual Machine Converter (MVMC) | Microsoft | workload | V2V, P2V | Free | No licence cost (retired product) | Was a free Microsoft download; retired in 2017 and no longer distributed or supported. | Not available from Microsoft any more. Use Azure Migrate, StarWind V2V Converter or Veeam instead. Listed here only because it is still widely referenced in older runbooks. | Cold - full outage for the whole copy | Both | Smb | Eol | Automatic driver / guest tools injection | Historically the official VMware-to-Hyper-V converter with VMware Tools removal and Hyper-V IC injection. | Retired, unsupported, and blocked by modern vSphere API/TLS versions. Do not design new work around it. | https://learn.microsoft.com/
Hyper-V native import / export & Live Migration | Microsoft | workload | V2V | Included | Included with Windows Server / Azure Local | Part of the Windows Server (Standard or Datacenter) or Azure Local licence you already own. | No extra licence. Note Azure Local bills per physical core per month through an Azure subscription; Windows Server is per-core with CALs. | Live - no guest downtime | Agentless | Large | Current | Live migration (no guest downtime); Agentless operation; API / CLI automation | Shared-nothing Live Migration moves running VMs between standalone hosts with zero downtime and no extra product. | Hyper-V family only. Cross-version moves are forward-only - you cannot import a VM into an older Hyper-V build. | https://learn.microsoft.com/windows-server/virtualization/hyper-v/
System Center Virtual Machine Manager (SCVMM) | Microsoft | workload | V2V | Paid | Licensed with System Center per 16-core pack | System Center Standard or Datacenter, licensed per physical core (packs of 2/16) on managed hosts. Often already owned under an Enterprise Agreement. | Buy System Center through an EA, CSP or MPSA. Datacenter edition is required for high VM density. SCVMM is one component of the suite. | Cold - full outage for the whole copy | Agentless | Large | Legacy | Wave / batch orchestration; Agentless operation; Network and IP mapping; API / CLI automation | Fabric management plus, in older builds, a bulk VMware-to-Hyper-V V2V wizard driven by PowerShell. | The built-in VMware V2V conversion was removed in SCVMM 2019 and later. On current builds treat SCVMM as the landing-zone manager, not the converter. | https://learn.microsoft.com/system-center/vmm/
Storage Migration Service | Microsoft | workload | P2V, P2C, V2V, V2C | Included | Included with Windows Server / Windows Admin Center | Windows Server role plus the free Windows Admin Center console. | Included with Windows Server 2019 and later. Windows Admin Center is a free download. | Warm - seeded online, short cutover window | Agentless | Mid | Current | Discovery and assessment; Wave / batch orchestration; Agentless operation; Programme reporting / audit trail | Purpose-built for file servers: inventories shares, copies data and ACLs, then cuts over by taking the old server name and IP. Handles Samba sources too. | File and print workloads only - it is not a general-purpose server converter. | https://learn.microsoft.com/windows-server/storage/storage-migration-service/
Nutanix Move | Nutanix | workload | V2V, C2V, V2C | Included | No charge to Nutanix customers | Free downloadable appliance for any customer with a Nutanix cluster under support. | Sign in to the Nutanix Support Portal with your cluster entitlement and download the Move appliance (OVA/QCOW2). No licence key. Support is covered by your existing AOS contract. | Warm - seeded online, short cutover window | Agentless | Enterprise | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; Automatic driver / guest tools injection; Network and IP mapping; Non-disruptive test migration; API / CLI automation | The default path off VMware onto AHV. Seeds data while the source VM is running, injects VirtIO drivers automatically, maps networks, and cuts over in a short window per wave. | The target must be Nutanix AHV or NC2. Reverse flows exist (AHV back to ESXi, and AHV to AWS) but they are secondary use cases, not the product's purpose. Guest OS support is narrower than generic block replication - check old Linux kernels and Windows Server 2008 R2. | https://www.nutanix.com/products/move
Nutanix Cloud Clusters (NC2) | Nutanix | workload | V2C, C2V | Paid | Nutanix Cloud Platform subscription plus bare-metal cloud instance cost | Nutanix software subscription (per core / per node) layered on Azure or AWS bare-metal instances which you pay for separately. | Buy NC2 capacity-based licences from Nutanix or via the Azure/AWS marketplace (which lets you draw down a committed cloud spend agreement). | Near-zero - continuous sync, minutes to cut over | Agentless | Enterprise | Current | Live migration (no guest downtime); Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; Rollback / failback after cutover | Same AHV stack on-prem and in cloud, so lift-and-shift needs no guest conversion and you can move back later. | Bare-metal instance minimums make small footprints expensive. | https://www.nutanix.com/products/nutanix-cloud-clusters
Migration Toolkit for Virtualization (MTV / Forklift) | Red Hat | workload | V2V | Included | Included with OpenShift Virtualization; upstream Forklift is free | Shipped as a supported Operator with the OpenShift Virtualization Engine / OpenShift subscription. The upstream Forklift project is Apache-licensed and free. | Buy OpenShift Virtualization Engine (per-core subscription, sold in core pairs) from Red Hat or a partner, then install the MTV Operator from OperatorHub. For labs, run upstream Forklift on OKD at no cost. | Warm - seeded online, short cutover window | Agentless | Enterprise | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; Automatic driver / guest tools injection; Network and IP mapping; API / CLI automation | Plan-and-wave migration into OpenShift Virtualization, warm migration with CBT from vSphere, automatic virt-v2v driver conversion, all declarative via CRDs. | Target must be OpenShift/KubeVirt. Storage class mapping and guest boot mode (BIOS vs UEFI) need care. | https://www.redhat.com/en/technologies/cloud-computing/openshift/virtualization
virt-v2v / virt-p2v (libguestfs) | Red Hat / libguestfs community | workload | V2V, P2V | Open source | No licence cost (GPL) | GPLv2 open source. Commercially supported when consumed through RHEL / OpenShift Virtualization subscriptions. | Install the libguestfs-tools / virt-v2v package from your distro repo. Free. For supported use, run it on a subscribed RHEL host. | Cold - full outage for the whole copy | Agentless | Mid | Current | Automatic driver / guest tools injection; API / CLI automation | The engine underneath most KVM-family migration tools. Rewrites the guest properly - installs VirtIO drivers, fixes bootloaders and fstab, removes VMware Tools. | CLI only, cold conversion, one VM per invocation. Wrap it in scripts (or use MTV / Proxmox import) for scale. | https://libguestfs.org/virt-v2v.1.html
oVirt / RHV VMware import (v2v-conversion-host) | Red Hat / oVirt community | workload | V2V | Open source | No licence cost | Apache 2.0 open source; RHV itself reached end of maintenance, oVirt continues as a community project. | Free. If you need vendor support, the supported path is now OpenShift Virtualization or Oracle Linux Virtualization Manager. | Cold - full outage for the whole copy | Agentless | Mid | Legacy | Automatic driver / guest tools injection; Wave / batch orchestration | Import VMs straight from a vCenter into the oVirt engine from the admin portal. | RHV is end-of-life; plan a path to OpenShift Virtualization or another KVM platform. | https://www.ovirt.org/
qemu-img | QEMU project | workload | V2V, P2V | Open source | No licence cost (GPL) | GPLv2 open source, part of QEMU. | Install the qemu-utils / qemu-img package. Free. | Cold - full outage for the whole copy | Agentless | Smb | Current | API / CLI automation | Converts between VMDK, VHD/VHDX, QCOW2, RAW and VDI. The lowest common denominator when nothing else will read the disk. | Disk format conversion only - it does nothing about guest drivers, boot config or VM metadata. | https://www.qemu.org/docs/master/tools/qemu-img.html
Clonezilla | NCHC Free Software Labs | workload | P2V, V2V | Open source | No licence cost (GPL) | GPLv2 open source live image. | Download the ISO. Free, including commercial use. | Cold - full outage for the whole copy | N/a | Smb | Current |  | Boot both sides from the live ISO and clone disk-to-disk over the network. Works when no agent can be installed and the OS is unusual or unsupported. | Full outage for the whole copy, manual driver and bootloader repair afterwards, no incremental sync. | https://clonezilla.org/
Proxmox VE ESXi import wizard & qm import | Proxmox Server Solutions | workload | V2V | Open source | Free; optional support subscription from ~EUR 115 per CPU socket per year | Proxmox VE is AGPLv3 and free to use, including the import wizard. Subscriptions buy the enterprise repository and support, not features. | Download the ISO and run it with no key. For production, buy a per-socket annual subscription (Community, Basic, Standard, Premium tiers) from Proxmox or a reseller and paste the key into the web UI. | Cold - full outage for the whole copy | Agentless | Mid | Current | Agentless operation; Automatic driver / guest tools injection; API / CLI automation | Since PVE 8.2 you can add an ESXi host as a storage source and import VMs straight from the web UI, with disk conversion handled for you. qm importovf / importdisk cover everything else. | Cold migration - the guest is off during the copy. No changed-block tracking, so a large VM means a long window. Windows guests need VirtIO drivers staged before the move. | https://pve.proxmox.com/wiki/Migrate_to_Proxmox_VE
Proxmox Backup Server | Proxmox Server Solutions | workload | V2V, P2V | Open source | Free; support subscription per CPU socket | AGPLv3, free. Optional paid subscription for the enterprise repo and support. | Same model as Proxmox VE - download free, buy a socket-based subscription for support. | Warm - seeded online, short cutover window | Both | Mid | Current | Changed-block tracking / incremental sync; Encryption in flight | Its bare-metal agent lets you back up a physical Windows/Linux server and restore it as a Proxmox VM - a workable free P2V route. | Restore-based, so expect a cutover window. | https://www.proxmox.com/en/products/proxmox-backup-server
Xen Orchestra V2V / VMware import | Vates (XCP-ng) | workload | V2V | Freemium | Free from source; Vates VMS subscription from roughly EUR 1,000 per host per year | Xen Orchestra is AGPLv3 - build from source for free with all features. Vates sells the prebuilt appliance plus support as a per-host annual subscription (Starter / Essential / Premium). | Either compile XO from GitHub at no cost, or buy a Vates Virtualization Management Stack subscription per host and get the signed appliance, updates and support. | Warm - seeded online, short cutover window | Agentless | Mid | Current | Agentless operation; Wave / batch orchestration; Automatic driver / guest tools injection; API / CLI automation | Built-in VMware import that reads from vCenter over the API and converts to XCP-ng, including a warm migration mode. | XCP-ng target only. Very large VMDKs and snapshots chains can be slow. | https://xen-orchestra.com/
XenServer Conversion Manager (XCM) | Cloud Software Group (XenServer) | workload | V2V | Included | Included with XenServer Premium / Citrix entitlement | Free appliance for customers with XenServer Premium Edition or a Citrix Virtual Apps and Desktops entitlement. | Download the XCM virtual appliance from the XenServer downloads page against your Citrix account, then point it at vCenter. Requires a licensed XenServer pool. | Cold - full outage for the whole copy | Agentless | Mid | Current | Wave / batch orchestration; Agentless operation; Automatic driver / guest tools injection; Network and IP mapping | Batch-converts VMware VMs into a XenServer pool with network mapping and guest tools handling. | Cold conversion, VMware source only. | https://docs.xenserver.com/
OpenStack Glance image import / Cinder migration | OpenInfra Foundation | workload | V2V, P2V, C2V | Open source | No licence cost; distro support is paid | Apache 2.0. Commercial distributions (Red Hat OpenStack Services on OpenShift, Canonical, Mirantis) are subscription-based per node or per core. | Upstream OpenStack is free. For supported builds, buy a per-socket/per-core subscription from Red Hat, Canonical or Mirantis. | Cold - full outage for the whole copy | Agentless | Large | Current | API / CLI automation; Wave / batch orchestration | Upload a converted QCOW2/RAW as a Glance image and boot it - fully scriptable and the standard landing path for private cloud. | You supply the conversion (virt-v2v/qemu-img) and the orchestration. | https://docs.openstack.org/
AWS Application Migration Service (MGN) | Amazon Web Services | workload | P2C, V2C, C2C | Free | Free for 90 days per source server; then about US$0.042 per server-hour | The service is free for 2,160 hours (90 days) per source server, which covers a normal migration. After that it bills per server-hour. You always pay for the staging-area EBS volumes, snapshots, data transfer and the target EC2 instances. | No purchase - enable AWS Application Migration Service in the target account and region. Install the free replication agent on each source server. Consider the AWS Migration Acceleration Program (MAP) for funding and credits. | Near-zero - continuous sync, minutes to cut over | Agent | Enterprise | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Non-disruptive test migration; Rollback / failback after cutover; Encryption in flight; API / CLI automation; Network and IP mapping | Continuous block-level replication from anything that runs the agent, unlimited non-disruptive test launches, and cutover measured in minutes. Source-agnostic, which makes it the strongest general P2C/V2C tool. | Agent-based - you need admin access and an outbound path to the staging subnet on every server. AWS target only. | https://aws.amazon.com/application-migration-service/
AWS VM Import/Export | Amazon Web Services | workload | V2C, C2V | Free | No service charge; you pay S3 storage and EBS | No service fee. You pay for the S3 bucket holding the image and the resulting EBS snapshots. | Nothing to buy. Use the AWS CLI import-image / export-image commands with an IAM role named vmimport. | Cold - full outage for the whole copy | Agentless | Smb | Current | API / CLI automation | Also works in reverse - export an EC2 instance back to OVA/VHD/VMDK, which is one of the few supported C2V routes out of AWS. | Cold, image-based, with significant export restrictions (instances originally imported, no marketplace AMIs). Slow for big disks. | https://docs.aws.amazon.com/vm-import/
AWS Elastic Disaster Recovery (DRS) | Amazon Web Services | workload | P2C, V2C, C2C | Paid | About US$0.028 per source server-hour plus storage | Consumption meter per replicating source server-hour, plus staging EBS and snapshots. | Enable in the AWS console; billed to the account. No commitment. | Near-zero - continuous sync, minutes to cut over | Agent | Enterprise | Current | Changed-block tracking / incremental sync; Non-disruptive test migration; Rollback / failback after cutover; Encryption in flight; API / CLI automation | Same engine as MGN but with point-in-time recovery and failback - use it when you need a rollback path to the source after cutover. | Costs from day one (no 90-day free period). | https://aws.amazon.com/disaster-recovery/
Google Migrate to Virtual Machines (M2VM) | Google Cloud | workload | V2C, P2C, C2C | Free | No charge for the migration service itself | Migrate to Virtual Machines is offered at no cost for migrations into Google Cloud. You pay only for the target Compute Engine resources, Persistent Disk and network egress. | Enable the vmmigration.googleapis.com API in your project and deploy the Migrate Connector OVA on-prem. Nothing to purchase. Ask your Google account team about the Rapid Migration Program (RaMP) for funding. | Near-zero - continuous sync, minutes to cut over | Both | Enterprise | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; Non-disruptive test migration; Encryption in flight; API / CLI automation; Discovery and assessment | Agentless from vSphere, wave-based groups, and test clones you can boot in an isolated VPC before cutover. Free. | Google Cloud target only; AWS/Azure sources use an agent. | https://cloud.google.com/migrate/virtual-machines
Google Cloud Migration Center | Google Cloud | assessment | V2C, P2C, C2C | Free | No charge | Free Google Cloud service. | Enable the API in your project. No cost. | Cold - full outage for the whole copy | Both | Enterprise | Current | Discovery and assessment; Application dependency mapping; Programme reporting / audit trail | Inventory, right-sizing, TCO modelling and group planning before you touch a workload. | Assessment only - hand off to M2VM for the move. | https://cloud.google.com/migration-center
OCI Cloud Migrations / Oracle Zero Downtime Migration | Oracle | workload, assessment | V2C, P2C, C2C | Free | Service is free; pay for target OCI resources | OCI Cloud Migrations (discovery, assessment, replication) and Zero Downtime Migration for databases are free OCI services. | Enable in your OCI tenancy. Oracle BYOL and Support Rewards can offset target licensing. No migration SKU to buy. | Near-zero - continuous sync, minutes to cut over | Both | Large | Current | Changed-block tracking / incremental sync; Discovery and assessment; Wave / batch orchestration; API / CLI automation; Programme reporting / audit trail | Free end-to-end tooling into OCI, and ZDM is the sanctioned route for Oracle Database estates with minimal downtime. | OCI target only; the VMware source path is less mature than Azure/AWS equivalents. | https://www.oracle.com/cloud/migration/
Alibaba Cloud Server Migration Center (SMC) | Alibaba Cloud | workload | P2C, V2C, C2C | Free | Free service; pay for target ECS and intermediate resources | No charge for SMC. You pay for the intermediate instance, disks and the destination ECS. | Activate SMC in the console, download the migration client, register the source servers. Nothing to purchase. | Warm - seeded online, short cutover window | Agent | Large | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; API / CLI automation | The native path into Alibaba Cloud, with incremental sync and image-based cutover. | Alibaba target only; documentation and support quality varies by region. | https://www.alibabacloud.com/help/en/smc
Huawei Cloud Server Migration Service (SMS) / Rainbow | Huawei Cloud | workload | P2C, V2C, C2C | Free | Free service; pay for target ECS/EVS | SMS is a free Huawei Cloud service; Rainbow adds assessment and application migration. | Enable in the Huawei Cloud console and install the SMS agent. No fee. | Warm - seeded online, short cutover window | Agent | Large | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Discovery and assessment; API / CLI automation | Block-level incremental replication into Huawei Cloud with a straightforward agent. | Huawei target only. | https://www.huaweicloud.com/intl/en-us/product/sms.html
IBM Turbonomic / IBM Cloud migration tooling | IBM | assessment | V2C, P2C, C2C, V2V | Paid | Subscription per managed workload/VM per month | Per-workload subscription (annual term), sold by IBM or partners. | Quote via IBM or the AWS/Azure marketplace listing. Sized on the number of managed entities. | Cold - full outage for the whole copy | Agentless | Enterprise | Current | Discovery and assessment; Application dependency mapping; Programme reporting / audit trail; API / CLI automation | Continuous right-sizing and placement analysis - strong for building the target sizing model and proving post-migration savings. | Analytics and automation, not a data mover. | https://www.ibm.com/products/turbonomic
OpenText PlateSpin Migrate | OpenText (Micro Focus / NetIQ) | workload | P2V, V2V, V2C, P2C, C2V, C2C | Paid | Perpetual per-workload licences, commonly bought in blocks | Licensed per workload, not per server or per host. Perpetual licences let you move the same workload as often as you need; there are also term/subscription options. The PlateSpin servers themselves are not separately licensed. | Buy workload licence blocks from OpenText or a partner and activate them in the PlateSpin Migrate licence manager (online or offline activation code). Size the block on the number of distinct workloads in the programme, not concurrency. | Near-zero - continuous sync, minutes to cut over | Both | Enterprise | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Non-disruptive test migration; Rollback / failback after cutover; Encryption in flight; Automatic driver / guest tools injection; API / CLI automation; Discovery and assessment; Programme reporting / audit trail | The most direction-agnostic mover on the market: any-to-any including V2P and cloud-back-to-on-prem. Server Sync, test cutover and scheduled waves are mature. | Licence cost, and a Windows-based control server to stand up. Check the supported-platform matrix for newer hypervisors such as AHV and Proxmox. | https://www.opentext.com/products/platespin-migrate
OpenText Migrate (Carbonite Migrate / Double-Take Move) | OpenText (Carbonite) | workload | P2V, V2V, V2C, P2C, C2V, C2C | Paid | Per-workload licence, perpetual or term | Licensed per migrated workload (source server). Perpetual and subscription options; often sold in 10/25-workload bundles. | Purchase per-workload licences from OpenText or a partner; activate the console with the supplied serial. Cloud marketplace listings exist for AWS and Azure. | Near-zero - continuous sync, minutes to cut over | Agent | Enterprise | Current | Changed-block tracking / incremental sync; Live migration (no guest downtime); Wave / batch orchestration; Non-disruptive test migration; Rollback / failback after cutover; Encryption in flight; API / CLI automation | Continuous byte-level replication at the OS layer, so the source stays fully online right up to a cutover measured in minutes. Hardware- and hypervisor-independent. | Agent on every source, and per-workload cost adds up on big estates. | https://www.opentext.com/products/carbonite-migrate
Zerto (HPE) | Hewlett Packard Enterprise (Zerto) | workload | V2V, V2C, C2V, C2C | Paid | Subscription per protected VM per month/year | Subscription licensed per protected VM (Enterprise Cloud Edition covers DR plus migration and long-term retention). Also available through HPE GreenLake. | Quote from HPE/Zerto or a partner, sized on protected VM count; keys applied in the Zerto Virtual Manager. Short-term migration licences are available for one-off programmes - ask specifically for them. | Near-zero - continuous sync, minutes to cut over | Agentless | Enterprise | Current | Changed-block tracking / incremental sync; Live migration (no guest downtime); Wave / batch orchestration; Non-disruptive test migration; Rollback / failback after cutover; Encryption in flight; Network and IP mapping; API / CLI automation | Continuous journal-based replication with seconds-level RPO and application-consistent multi-VM protection groups. Move a whole multi-tier application as one unit, test it, then commit or roll back. | Priced as a DR product. Hypervisor-level replication means source must be vSphere or Hyper-V. | https://www.zerto.com/
Cloudbase Coriolis | Cloudbase Solutions | workload | V2V, V2C, C2V, C2C | Paid | Per-migrated-VM licensing; free trial available | Commercial per-VM licensing with support; a free evaluation covers a limited number of migrations. | Request a quote from Cloudbase Solutions sized on the number of VMs in the programme. Delivered as an appliance. | Warm - seeded online, short cutover window | Agentless | Large | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; API / CLI automation; Automatic driver / guest tools injection; Network and IP mapping | Genuinely bidirectional cloud-to-cloud and cloud-to-on-prem. One of the few tools that treats C2V as a first-class scenario rather than an afterthought. | Smaller vendor, so validate your exact source/target pair in a PoC first. | https://cloudbase.it/coriolis/
RackWare RMM | RackWare | workload | P2V, V2V, V2C, P2C, C2V, C2C | Paid | Per-workload subscription; also sold via cloud marketplaces | Subscription per migrated workload, term based. Available on the AWS, Azure, OCI and IBM Cloud marketplaces so it can draw down committed cloud spend. | Buy directly or through the cloud marketplace listing (which often counts against an existing cloud commitment). Licence applies to the RMM appliance. | Near-zero - continuous sync, minutes to cut over | Agentless | Enterprise | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; Non-disruptive test migration; Encryption in flight; API / CLI automation; Discovery and assessment | Agentless (SSH/WMI based) any-to-any mover with strong Linux support and genuine cloud-to-on-prem repatriation. | Needs credentialed access to every source; niche vendor. | https://www.rackwareinc.com/
Hystax Acura | Hystax | workload | V2C, P2C, C2V, C2C, V2V | Paid | Per-VM subscription, quote based | Per-workload subscription; often sold through cloud providers as a white-labelled migration service. | Quote from Hystax or via a partner cloud provider. | Near-zero - continuous sync, minutes to cut over | Agent | Large | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Non-disruptive test migration; Rollback / failback after cutover; API / CLI automation | Consistent multi-VM replication groups with automated test runs; strong in OpenStack and sovereign-cloud scenarios. | Less well known; validate support coverage in your region. | https://hystax.com/
Veeam Data Platform (Backup & Replication) | Veeam Software | workload | P2V, V2V, V2C, P2C, C2V, C2C | Paid | Veeam Universal Licence (VUL), typically sold in 10-instance packs | Veeam Universal Licence - portable instances that can be applied to VMs, physical servers, cloud instances or workstations. Per-socket perpetual licences still exist for legacy estates but VUL is the current model. | Buy VUL instance packs (annual subscription, 1/3/5 year) from Veeam or a ProPartner, or via the AWS/Azure marketplace. A licence file is uploaded to the Veeam console. Veeam Community Edition is free for up to 10 instances and can do cross-platform Instant Recovery - enough for a small migration. | Warm - seeded online, short cutover window | Both | Enterprise | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; Non-disruptive test migration; Rollback / failback after cutover; Encryption in flight; Automatic driver / guest tools injection; API / CLI automation; Programme reporting / audit trail | If you already own Veeam you already own a cross-platform mover. Instant Recovery restores a backup of anything as a VM on vSphere, Hyper-V, AHV or Proxmox, and Direct Restore to Azure/EC2/GCP covers V2C. One backup, many possible targets. | Restore-based, so cutover means a full or seeded restore plus a final incremental - plan the window. Not a continuous-replication tool for zero-downtime moves. | https://www.veeam.com/products/veeam-data-platform.html
Veeam Agent for Windows / Linux (FREE edition) | Veeam Software | workload | P2V, P2C | Free | No licence cost for the FREE edition | Veeam Agent FREE edition - no licence key, no expiry, full bare-metal recovery. | Download from Veeam with a free account. The FREE edition covers volume-level backup and bare-metal restore, which is all a manual P2V needs. Paid editions add central management through the Veeam console. | Cold - full outage for the whole copy | Agent | Smb | Current | Automatic driver / guest tools injection | Back up the physical server, boot the recovery media inside an empty VM, restore. A reliable, genuinely free P2V for a handful of machines. | Manual, one machine at a time, and the restore window is a full outage. | https://www.veeam.com/windows-endpoint-server-backup-free.html
NAKIVO Backup & Replication | NAKIVO | workload | V2V, P2V, V2C | Paid | Per-socket or per-workload perpetual/subscription; free trial and a free edition for small use | Perpetual per-socket (hypervisor hosts) or per-workload subscription. NAKIVO also offers a limited free edition. | Buy from NAKIVO or a reseller and apply the licence in the Director web console. Sizing is per CPU socket on the source hosts or per protected workload. | Warm - seeded online, short cutover window | Both | Mid | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; Encryption in flight; Rollback / failback after cutover | Notably cheaper than the tier-one backup vendors, with cross-platform recovery that covers Proxmox and AHV - handy for mid-market VMware exits. | Restore-based migration; smaller ecosystem. | https://www.nakivo.com/
Vinchin Backup & Recovery | Vinchin | workload | V2V, P2V, V2C | Paid | Per-socket / per-host perpetual or subscription; 60-day full-feature trial | Perpetual or subscription, licensed per CPU socket or per host depending on edition (Essential / Standard / Enterprise). | Request a quote and a 60-day trial key from Vinchin or a regional reseller; the trial is fully featured and is often long enough to complete a small migration outright. | Warm - seeded online, short cutover window | Both | Mid | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; Automatic driver / guest tools injection | Supports an unusually wide list of hypervisors including Chinese platforms (Huawei FusionCompute, H3C CAS, Sangfor HCI, oVirt, OLVM) that the big vendors ignore. Explicit V2V migration workflow. | Restore/replica based; support presence varies outside APAC and EMEA. | https://www.vinchin.com/vm-migration.html
Storware Backup & Recovery (vProtect) | Storware | workload | V2V | Paid | Per-VM or per-socket subscription | Subscription licensed per protected VM or per CPU socket. | Quote from Storware or a partner; licence file applied in the Storware console. | Warm - seeded online, short cutover window | Agentless | Mid | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; API / CLI automation | Built specifically for the open-source and alternative hypervisor world - restore a VMware backup directly into AHV, Proxmox, OpenStack or KubeVirt. | Smaller vendor; confirm your exact platform versions. | https://storware.eu/
Commvault Cloud (Complete Backup & Recovery) | Commvault | workload | V2V, P2V, V2C, C2V, C2C | Paid | Per-TB front-end or per-VM subscription | Subscription by front-end terabyte or per-VM/per-instance, depending on the package. | Quote through Commvault or a partner; also on AWS/Azure marketplaces for cloud-spend drawdown. | Warm - seeded online, short cutover window | Both | Enterprise | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; Non-disruptive test migration; Encryption in flight; API / CLI automation; Programme reporting / audit trail; Discovery and assessment | Genuine any-to-any conversion on restore across a very wide platform matrix, including UNIX, and strong reporting for audit-heavy programmes. | Complex to set up if you do not already run it; licensing needs careful sizing. | https://www.commvault.com/
Cohesity DataProtect (incl. Veritas NetBackup) | Cohesity | workload | V2V, V2C, P2V | Paid | Per-TB or per-workload subscription | Capacity or workload-based subscription. | Quote through Cohesity or a partner. | Warm - seeded online, short cutover window | Both | Enterprise | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; Encryption in flight; API / CLI automation; Programme reporting / audit trail | Cross-hypervisor recovery plus instant mount for validation; NetBackup adds deep UNIX and mainframe-adjacent coverage. | Backup-first product; migration is a recovery workflow. | https://www.cohesity.com/
Rubrik Security Cloud | Rubrik | workload | V2V, V2C | Paid | Per-TB subscription | Capacity-based subscription. | Quote through Rubrik or a partner. | Warm - seeded online, short cutover window | Both | Enterprise | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; Encryption in flight; API / CLI automation | Fast instant recovery and CloudOn conversion of on-prem backups into cloud instances. | Positioned for cyber-resilience; migration is a side benefit. | https://www.rubrik.com/
Dell PowerProtect Data Manager | Dell Technologies | workload | V2V, V2C | Paid | Per-TB subscription or perpetual | Front-end capacity licensing, often bundled with PowerProtect appliances. | Quote via Dell or a partner. | Warm - seeded online, short cutover window | Both | Enterprise | Current | Changed-block tracking / incremental sync; Wave / batch orchestration; Agentless operation; Encryption in flight; API / CLI automation | Natural fit where the estate is already Dell/VxRail. | Migration is restore-driven; narrower alternative-hypervisor support. | https://www.dell.com/en-us/dt/data-protection/powerprotect-data-manager.htm
Acronis Cyber Protect (Universal Restore) | Acronis | workload | P2V, V2V, V2C, P2C | Paid | Per-workload annual subscription | Per-workload (server / workstation / VM host) annual subscription; perpetual available in some regions. | Buy per-workload licences from Acronis or an MSP partner and register them in the Acronis console. | Warm - seeded online, short cutover window | Agent | Mid | Current | Changed-block tracking / incremental sync; Automatic driver / guest tools injection; Encryption in flight; Wave / batch orchestration | Universal Restore injects the right HAL and storage drivers so an image taken from physical hardware boots cleanly as a VM - the classic answer for awkward legacy servers. | Per-workload cost, and the console is aimed at MSPs rather than large enterprise programmes. | https://www.acronis.com/
Macrium Reflect (ReDeploy) | Paramount Software (Macrium) | workload | P2V, V2V | Paid | Per-machine perpetual or subscription; the old Free edition was retired | Per-machine licence (Home / Workstation / Server editions). Macrium Reflect Free was discontinued in January 2024. | Buy per-machine licences from Macrium; a 30-day trial covers a one-off migration. | Cold - full outage for the whole copy | Agent | Smb | Current | Automatic driver / guest tools injection | ReDeploy fixes the boot-critical drivers when restoring a Windows image onto different (virtual) hardware. Fast and dependable for small numbers. | Windows only, no orchestration, no free tier any more. | https://www.macrium.com/
AOMEI Backupper / Centralized Backupper | AOMEI Technology | workload | P2V, V2V | Freemium | Free Standard edition; Workstation/Server editions are paid per machine | Free edition for basic imaging; Universal Restore (dissimilar hardware) requires a paid Professional/Server licence. | Download the free edition, buy a per-machine key online to unlock Universal Restore and centralized management. | Cold - full outage for the whole copy | Agent | Smb | Current | Automatic driver / guest tools injection | Low cost, straightforward image-and-restore P2V for SMB Windows estates. | Not an enterprise tool - no wave management, limited Linux support. | https://www.aomeitech.com/
StarWind V2V Converter / P2V Converter | StarWind Software | workload | V2V, P2V | Free | Completely free, including commercial use | Free product. No paid tier, no feature gating, no per-VM limit. | Fill in the download form on the StarWind site and you get the installer. No key to manage. | Warm - seeded online, short cutover window | Both | Mid | Current | Wave / batch orchestration; Automatic driver / guest tools injection; API / CLI automation | Converts between VMDK, VHD/VHDX, QCOW2, RAW and StarWind IMG, with a CLI for scripting, multi-VM batches and a hot-migration mode. The most capable genuinely free converter for VMware-to-Proxmox and VMware-to-Hyper-V work. | No central orchestration console or wave reporting; you drive it per batch. | https://www.starwindsoftware.com/starwind-v2v-converter
Paragon Hard Disk Manager (P2V) | Paragon Software Group | workload | P2V, V2V | Paid | Per-machine licence | Per-machine perpetual licence (Business / Technician editions). | Buy online from Paragon; Technician licence covers servicing multiple machines. | Cold - full outage for the whole copy | Agent | Smb | Current | Automatic driver / guest tools injection | P2V Copy and P2V Adjust OS handle awkward legacy Windows builds. | Small-scale, Windows-centric. | https://www.paragon-software.com/
Scale Computing Move / HyperCore VM import | Scale Computing | workload | V2V, P2V | Included | Included with SC//HyperCore licensing | Included for customers with a Scale Computing cluster under support. | Download from the Scale Computing portal against your cluster entitlement; no separate purchase. | Warm - seeded online, short cutover window | Both | Mid | Current | Wave / batch orchestration; Automatic driver / guest tools injection; Network and IP mapping | Purpose-built for edge and retail estates moving off VMware onto HyperCore, with a simple import wizard. | Scale Computing target only. | https://www.scalecomputing.com/
VergeOS VM import / VMware migration | Verge.io | workload | V2V | Included | Included with the VergeOS subscription | Included with the VergeOS per-node subscription. | Comes with the platform; no separate migration SKU. | Cold - full outage for the whole copy | Agentless | Mid | Current | Wave / batch orchestration; Automatic driver / guest tools injection | Built-in importer that pulls VMs from vCenter into VergeOS tenants. | VergeOS target only; smaller vendor. | https://www.verge.io/
HPE VM Essentials VM conversion | Hewlett Packard Enterprise | workload | V2V | Included | Included with the HPE VM Essentials socket subscription | Included with the per-socket HPE VM Essentials software subscription. | Purchase HPE VM Essentials per CPU socket (1/3/5 year) from HPE or a partner; migration tooling is part of the platform. | Cold - full outage for the whole copy | Agentless | Mid | Current | Wave / batch orchestration; Automatic driver / guest tools injection; API / CLI automation | Low-cost per-socket KVM platform aimed squarely at VMware exits, with conversion built in. | Newer product - validate the guest OS matrix. | https://www.hpe.com/
Sangfor HCI aSV VM converter | Sangfor Technologies | workload | V2V, P2V | Included | Included with Sangfor HCI licensing | Included with the Sangfor HCI platform licence. | Provided with the platform through Sangfor or a regional partner. | Cold - full outage for the whole copy | Both | Mid | Current | Wave / batch orchestration; Automatic driver / guest tools injection | Native converter for organisations standardising on Sangfor HCI, common across APAC and the Middle East. | Sangfor target only. | https://www.sangfor.com/
Huawei Rainbow migration suite | Huawei | workload, assessment | V2V, P2V, V2C, P2C | Included | Provided with Huawei platform engagements | Supplied with Huawei FusionCompute / Huawei Cloud engagements. | Obtain through Huawei or a certified partner as part of the platform project. | Warm - seeded online, short cutover window | Agent | Large | Current | Discovery and assessment; Changed-block tracking / incremental sync; Wave / batch orchestration | Assessment plus replication into Huawei platforms, with strong regional support. | Huawei targets only. | https://www.huawei.com/
Oracle VirtualBox OVF import/export | Oracle | workload | V2V | Freemium | Base package free (GPLv3); the Extension Pack needs a licence for commercial use | VirtualBox base is GPLv3 and free. The Oracle VM VirtualBox Extension Pack is free for personal/evaluation use only - commercial use requires a per-socket Oracle licence (Oracle VM VirtualBox Enterprise). | Download the base package freely. If you deploy the Extension Pack in a business, buy VirtualBox Enterprise per socket from Oracle - this is a common and expensive audit finding. | Cold - full outage for the whole copy | Agentless | Smb | Current | API / CLI automation | Handy lab and developer-workstation path in and out of OVF/OVA. | Not a server migration tool. Watch the Extension Pack licensing trap. | https://www.virtualbox.org/
RVTools | Dell Technologies (Robware) | assessment | V2V, V2C, C2V | Free | No licence cost | Free tool, now distributed by Dell after acquiring Robware. | Download from robware.net (Dell account sign-in). Free for any use. | Cold - full outage for the whole copy | Agentless | Enterprise | Current | Discovery and assessment; Programme reporting / audit trail | One click gives you a complete vSphere inventory in Excel - VMs, disks, snapshots, tools versions, hosts, networks. The standard first step of any VMware exit. | vSphere only, read-only, point-in-time snapshot of inventory. | https://www.robware.net/
Live Optics | Dell Technologies | assessment | P2V, V2V, V2C, P2C | Free | No licence cost | Free SaaS assessment service. | Register a free account and run the collector. No cost - Dell uses it as a pre-sales sizing tool. | Cold - full outage for the whole copy | Agentless | Enterprise | Current | Discovery and assessment; Programme reporting / audit trail | Performance profiling over a 7-day window (IOPS, throughput, latency, CPU) - the data you need to size the target platform rather than just copy the current allocation. | Data is uploaded to Dell's cloud; check this against your data-handling policy. | https://www.liveoptics.com/
Device42 (Freshworks) | Freshworks (Device42) | assessment | P2V, V2V, V2C, P2C, C2V, C2C | Paid | Annual subscription by device count | Annual subscription sized on managed devices. | Quote from Device42/Freshworks or a partner; free trial available. | Cold - full outage for the whole copy | Both | Enterprise | Current | Discovery and assessment; Application dependency mapping; Programme reporting / audit trail; API / CLI automation | Agentless discovery with application dependency mapping and move-group generation - the answer to "what talks to what, and what must move together". | Assessment and planning only. | https://www.device42.com/
Faddom | Faddom | assessment | V2V, V2C, P2C | Paid | Subscription by server count; free tier for small estates | Subscription by number of servers; a free tier covers small environments. | Self-service sign-up with a free tier, then upgrade by server count. | Cold - full outage for the whole copy | Agentless | Mid | Current | Discovery and assessment; Application dependency mapping; Programme reporting / audit trail | Fully agentless dependency mapping that stands up in about an hour - good when you cannot get agents approved. | Mapping only. | https://faddom.com/
Flexera One (Cloud Migration & Optimization) | Flexera | assessment | V2C, P2C, C2C | Paid | Enterprise subscription, quote based | Enterprise SaaS subscription. | Quote from Flexera. | Cold - full outage for the whole copy | Both | Enterprise | Current | Discovery and assessment; Application dependency mapping; Programme reporting / audit trail; API / CLI automation | Ties discovery to software licence entitlement - critical when moving Oracle, SQL Server or SAP where the target platform changes the licence position. | Expensive; overkill unless licence risk is the driver. | https://www.flexera.com/
Active Directory Migration Tool (ADMT 3.2) | Microsoft | ad |  | Free | No licence cost | Free Microsoft download, covered by your existing Windows Server licensing. | Download ADMT 3.2 from the Microsoft Download Center. Free. Note it has not been updated since Windows Server 2012 R2 - it installs on newer servers only with documented workarounds, and it needs a SQL Server (Express is fine) instance. | Warm - seeded online, short cutover window | Agent | Mid | Legacy | SID history; Password migration / sync; Coexistence during migration; Object-level rollback | The only free tool that does real inter-forest migration with SID history and password export. Migrates users, groups, computers and service accounts, and re-ACLs member servers. | Unchanged since 2012 R2 and effectively in maintenance. Requires a two-way trust, is one-directional (no ongoing coexistence), has no GUI for large waves, and there is no built-in rollback - you must plan restores. Expect scripting. | https://learn.microsoft.com/troubleshoot/windows-server/active-directory/admt-guide-migrating-restructuring-active-directory-domains
Quest Migration Manager for Active Directory | Quest Software | ad |  | Paid | Per-user perpetual or term licence, quote based | Licensed per migrated user/account, perpetual or term, with separate maintenance. | Quote from Quest or a Quest partner, sized on the number of enabled user accounts to migrate. Licence keys are applied in the Quest console. Ask about short-term project licences - AD migrations are finite and Quest will price a 12-month term. | Near-zero - continuous sync, minutes to cut over | Agent | Enterprise | Current | SID history; Password migration / sync; Coexistence during migration; Object-level rollback; Directory synchronisation; Programme reporting / audit trail; Delegated administration | Two-way directory synchronisation means source and target coexist for months while you migrate in waves. Resource updating re-ACLs servers and workstations automatically, and you can roll a user back. | Needs agents on domain controllers and a trust; licence cost is the main objection versus ADMT. | https://www.quest.com/products/migration-manager-for-active-directory/
Quest On Demand Migration for Active Directory / Entra ID | Quest Software | ad |  | Paid | SaaS, per-user subscription, quote based | SaaS subscription licensed per migrated user/device, term based. | Purchased as a term subscription through Quest or a partner; entitlements appear in the On Demand tenant. Sized per user and per device. | Near-zero - continuous sync, minutes to cut over | Both | Enterprise | Current | Coexistence during migration; Directory synchronisation; Password migration / sync; Programme reporting / audit trail; Workstation / device migration; Multi-tenant / multi-forest | No trust and no on-prem migration servers required. Handles AD-to-AD, AD-to-Entra ID and tenant-to-tenant, with device (Entra join) migration in the same workflow - the modern M&A answer. | SaaS, so your directory metadata transits a Quest-hosted service. Per-user cost. | https://www.quest.com/products/on-demand-migration/active-directory/
Quest Migrator Pro for Active Directory (Binary Tree) | Quest Software (Binary Tree) | ad |  | Paid | Per-user / per-device licence, quote based | Per-user and per-device licensing, term or perpetual. | Quote from Quest or a partner. Sized on accounts plus the number of workstations to be re-domained. | Near-zero - continuous sync, minutes to cut over | Agent | Enterprise | Current | SID history; Coexistence during migration; Directory synchronisation; Workstation / device migration; Programme reporting / audit trail | Its real differentiator is zero-touch workstation domain moves - the endpoint agent re-joins the device, remaps the profile and handles BitLocker, with self-service scheduling for the user. | Endpoint agent deployment is a project in itself. | https://www.quest.com/products/migrator-pro-for-active-directory/
Microsoft Entra Connect Sync / Cloud Sync | Microsoft | ad |  | Free | No licence cost; needs Entra ID (free tier works for basic sync) | Free tooling. Password hash sync and pass-through auth work on the Entra ID Free tier; group writeback, password writeback and Entra ID Protection need Entra ID P1/P2. | Download Entra Connect from Microsoft. Cloud Sync is agent-based and configured in the Entra portal. Buy Entra ID P1 only if you need writeback or conditional access. | Live - no guest downtime | Agent | Enterprise | Current | Directory synchronisation; Password migration / sync; Coexistence during migration; Multi-tenant / multi-forest | Cloud Sync supports multiple disconnected forests to one tenant, which is exactly the shape of an M&A estate that has not been consolidated yet. | Synchronisation, not migration - it does not move SID history or re-ACL resources. | https://learn.microsoft.com/entra/identity/hybrid/
Microsoft Entra cross-tenant synchronization | Microsoft | ad |  | Included | Requires Entra ID P1 or higher for synchronised users | Feature of Entra ID; each synchronised user must be covered by an Entra ID P1 (or higher) licence in the source tenant. | Included with Microsoft 365 E3/E5 or Entra ID P1 bought standalone per user per month. | Live - no guest downtime | Agentless | Enterprise | Current | Directory synchronisation; Coexistence during migration; Multi-tenant / multi-forest | Provisions B2B member accounts into the target tenant automatically, giving day-one access to Teams and SharePoint during a long merger. | Creates guest/member objects, it does not migrate mailboxes or data. Pair it with a mailbox tool. | https://learn.microsoft.com/entra/identity/multi-tenant-organizations/
Microsoft Identity Manager (MIM) | Microsoft | ad |  | Paid | Server licence plus MIM CAL per managed user | MIM server licence (or a Windows Server licence covering it) plus a MIM CAL for each managed user, commonly obtained via Microsoft 365 E3/E5 or Entra ID P1 which include MIM CAL rights. | Check your EA - if you hold Entra ID P1/P2 or M365 E3/E5 you very likely already have MIM CAL rights and only need the server licence. | Live - no guest downtime | Agentless | Enterprise | Legacy | Directory synchronisation; Coexistence during migration; Password migration / sync; Delegated administration | Rules-based multi-forest GALSync and account provisioning where the coexistence period runs for years rather than months. | Heavy to build and operate; no SID history. The strategic direction from Microsoft is Entra, so treat MIM as a bridge. | https://learn.microsoft.com/microsoft-identity-manager/
ForensiT User Profile Wizard / Transwiz | ForensiT | ad |  | Freemium | Personal edition free; Corporate/Professional editions per seat | Free Personal edition for single machines. Corporate and Professional editions are licensed per workstation (volume pricing) and add scripted, unattended and Entra-join migration. | Buy a per-seat Corporate licence from ForensiT sized on workstation count; licences are perpetual for the version purchased. | Warm - seeded online, short cutover window | Agent | Large | Current | Workstation / device migration | Very cost-effective way to re-domain thousands of Windows endpoints and keep the user profile, mapped drives, Outlook profile and desktop intact. Also handles domain-to-Entra-join. | Endpoints only - it does nothing for the directory itself. Pair with ADMT or Quest. | https://www.forensit.com/domain-migration.html
ManageEngine ADManager Plus | Zoho (ManageEngine) | ad |  | Paid | Annual subscription by domain/helpdesk technician count; free edition for small use | Annual subscription (Standard / Professional) sized on domains and technicians. A free edition covers up to 100 objects. | Buy online or via a partner; licence applied in the web console. | Warm - seeded online, short cutover window | Agentless | Mid | Current | Programme reporting / audit trail; Delegated administration; Directory synchronisation | Bulk object creation, CSV-driven provisioning and strong reporting - useful for the "rebuild rather than migrate" pattern in small consolidations. | No SID history, no trust-based migration. It is an administration tool doing migration work. | https://www.manageengine.com/products/ad-manager/
Netwrix GroupID / Directory Manager | Netwrix | ad |  | Paid | Per-user annual subscription | Per-managed-user subscription. | Quote from Netwrix or a partner. | Warm - seeded online, short cutover window | Agentless | Mid | Current | Directory synchronisation; Programme reporting / audit trail; Delegated administration | Identity lifecycle and group cleanup - most valuable in the pre-migration hygiene phase where you decide what not to bring across. | Not a SID-history migration engine. | https://www.netwrix.com/
Semperis Directory Services Protector & ADFR | Semperis | ad |  | Paid | Per-user annual subscription | Annual subscription sized on AD user accounts. | Quote from Semperis or a partner. | Live - no guest downtime | Agent | Enterprise | Current | Object-level rollback; Programme reporting / audit trail | Not a migration tool, but the safety net around one: object-level rollback and full forest recovery if a migration wave corrupts the directory. Also surfaces the security debt you should fix before consolidating. | Adds cost without moving anything. Justify it on risk. | https://www.semperis.com/
Cayosoft Guardian / Administrator | Cayosoft | ad |  | Paid | Per-user annual subscription | Per-user subscription. | Quote from Cayosoft or a partner. | Live - no guest downtime | Agentless | Mid | Current | Object-level rollback; Directory synchronisation; Programme reporting / audit trail; Multi-tenant / multi-forest | Unified hybrid AD/Entra administration and change rollback during a long coexistence. | Administration-centric. | https://www.cayosoft.com/
BitTitan MigrationWiz - Active Directory & DeploymentPro | BitTitan | ad |  | Paid | Per-user licence, typically around US$12-15 per user for the AD/device component | Prepaid per-user licences bought from the BitTitan store; each licence covers one user for a 12-month window with unlimited passes. | Buy licences online with a card or PO and apply them to users in the MigrationWiz portal. No infrastructure, no contract minimum - which is why MSPs favour it. | Near-zero - continuous sync, minutes to cut over | Agent | Mid | Current | Directory synchronisation; Workstation / device migration; Coexistence during migration; Multi-tenant / multi-forest | Transparent, self-service pricing and no on-prem servers. DeploymentPro reconfigures Outlook profiles on endpoints automatically at cutover. | Lighter than Quest for complex forest surgery - no SID history. | https://www.bittitan.com/
Exchange Hybrid Configuration Wizard + native move requests (MRS) | Microsoft | exchange |  | Included | No extra cost beyond Exchange / Microsoft 365 licences | Included with Exchange Server and Microsoft 365. A free Hybrid Edition Exchange Server key is available for the hybrid management server so you do not pay for that instance. | Run the Hybrid Configuration Wizard from the Microsoft 365 admin centre. Request the free Hybrid Edition product key from the Microsoft hybrid key portal for the on-prem hybrid server. Target mailboxes need an Exchange Online Plan 1/2 or M365 licence. | Near-zero - continuous sync, minutes to cut over | Agentless | Enterprise | Current | Coexistence during migration; Cross-org free/busy and GAL sync; Delta / incremental passes; Programme reporting / audit trail | The only method Microsoft fully supports for a phased Exchange-to-Exchange Online move. Full free/busy, mail routing and a single GAL during coexistence, and mailboxes move online with only a brief Outlook restart. | Requires an on-prem Exchange server, Entra Connect, certificates and published autodiscover. Throttling makes very large estates slow, and there is no reporting dashboard worth the name. | https://learn.microsoft.com/exchange/hybrid-deployment/hybrid-deployment
Microsoft 365 Cross-Tenant Mailbox Migration (native) | Microsoft | exchange |  | Included | No per-mailbox fee; both tenants need appropriate M365 licences | Native Exchange Online feature. No migration SKU; source and target users must hold Exchange Online / Microsoft 365 licences. | Configure a cross-tenant migration Entra application and mailbox migration endpoint with the ExchangeOnlineManagement PowerShell module. Nothing to buy. Note Microsoft has signalled licence requirements around some cross-tenant capabilities - confirm current terms for your tenants. | Near-zero - continuous sync, minutes to cut over | Agentless | Enterprise | Current | Delta / incremental passes; Coexistence during migration; Programme reporting / audit trail | Moves the mailbox itself rather than copying items, so nothing is re-ingested and no per-mailbox fee is paid. Best fidelity available for tenant-to-tenant. | PowerShell only - no GUI, no scheduling, no progress dashboard. Does not move OneDrive, SharePoint, Teams chat or Power Platform. Target addresses must be pre-staged as MailUsers. | https://learn.microsoft.com/microsoft-365/enterprise/cross-tenant-mailbox-migration
Exchange Admin Center migration (cutover / staged / IMAP) | Microsoft | exchange |  | Included | Included with Microsoft 365 | Included with the Microsoft 365 subscription. | Use the migration section of the Exchange admin centre. No cost. Target mailboxes need M365 licences. | Warm - seeded online, short cutover window | Agentless | Smb | Current | Delta / incremental passes | Zero-cost route for estates under roughly 150 mailboxes. Cutover migration moves everything in one pass over a weekend. | Cutover is practically capped around 150 mailboxes and forces one big-bang weekend. IMAP migration brings mail only - no calendar, contacts or tasks. | https://learn.microsoft.com/exchange/mailbox-migration/mailbox-migration
Google Workspace Data Migration Service | Google | exchange |  | Included | Included with Google Workspace | Included with a Google Workspace subscription. | Run it from the Google Admin console. No extra charge. | Warm - seeded online, short cutover window | Agentless | Mid | Current | Delta / incremental passes | Free path into Google Workspace from Exchange, Microsoft 365 or IMAP. | One-way into Google, mail/calendar/contacts only, limited throughput and error reporting. | https://support.google.com/a/answer/6251069
BitTitan MigrationWiz | BitTitan | exchange |  | Paid | Roughly US$15 per mailbox; User Migration Bundle around US$25 per user (adds OneDrive/Drive) | Prepaid per-user licences. A Mailbox Migration licence covers one source-to-target mailbox move with unlimited delta passes for 12 months. The User Migration Bundle adds documents and personal archives. | Buy licences self-service in the BitTitan store with a credit card or PO - no contract, no minimum, no infrastructure. Apply them to users in the MigrationWiz portal. Unused licences stay valid, so buying a block up front is normal. | Near-zero - continuous sync, minutes to cut over | Agentless | Enterprise | Current | Delta / incremental passes; Wave / batch orchestration; Programme reporting / audit trail; Coexistence during migration; Multi-tenant / multi-forest; Workstation / device migration | The widest source list in the market - Exchange 2010 onwards, M365, Google, IMAP, Zimbra, GroupWise, Notes, POP. Fully SaaS with no servers to build, transparent pricing, and DeploymentPro fixes Outlook profiles on endpoints at cutover. | Item-level copy, so very large mailboxes and archives take multiple passes and hit throttling. No free/busy coexistence of its own - pair it with Entra cross-tenant sync for that. | https://www.bittitan.com/migrationwiz/
Quest On Demand Migration for Email (ODME) | Quest Software | exchange |  | Paid | Quote-based per-user subscription, typically above BitTitan for equivalent scope | Per-user term subscription covering mailbox, OneDrive, SharePoint, Teams and Entra objects depending on the modules purchased. | Quote through Quest or a partner, sized per user and per module. Entitlements land in your On Demand tenant. Negotiate module bundles - buying mailbox, OneDrive and Teams separately is much more expensive. | Near-zero - continuous sync, minutes to cut over | Agentless | Enterprise | Current | Delta / incremental passes; Wave / batch orchestration; Coexistence during migration; Cross-org free/busy and GAL sync; Programme reporting / audit trail; Multi-tenant / multi-forest | The strongest option for complex M&A: mailbox, OneDrive, SharePoint, Teams and identity in one console, with cross-tenant free/busy and GAL coexistence while the move runs for months. | No public pricing and enterprise-level cost. Overkill for a straightforward sub-500-seat move. | https://www.quest.com/products/on-demand-migration/
Quest Migration Manager for Exchange | Quest Software | exchange |  | Paid | Per-mailbox perpetual or term licence | Per-mailbox licensing with maintenance. | Quote from Quest or a partner sized on mailbox count. | Near-zero - continuous sync, minutes to cut over | Agent | Enterprise | Current | Delta / incremental passes; Coexistence during migration; Cross-org free/busy and GAL sync; Programme reporting / audit trail | Built for on-prem-to-on-prem consolidation across untrusted forests, with calendar and free/busy synchronisation during a long coexistence. | On-prem oriented; for cloud targets use On Demand Migration instead. | https://www.quest.com/products/migration-manager-for-exchange/
Quest Notes Migrator for Exchange (CMT) | Quest Software (Binary Tree) | exchange |  | Paid | Per-mailbox licence, quote based | Per-mailbox licensing. | Quote from Quest or a partner. | Warm - seeded online, short cutover window | Agent | Enterprise | Current | Delta / incremental passes; Coexistence during migration; Cross-org free/busy and GAL sync; Programme reporting / audit trail | The reference tool for HCL Notes/Domino and GroupWise estates, including mail-in databases, doclinks and application data. | Niche and expensive - but there is little competition for Notes. | https://www.quest.com/products/notes-migrator-for-exchange/
CodeTwo Exchange Migration / Office 365 Migration | CodeTwo | exchange |  | Paid | One-time per-mailbox licence, commonly a few US$ per mailbox with volume tiers | One-time perpetual per-mailbox licence (not a subscription), with volume discounts and a free trial limited by item count. | Buy online from CodeTwo sized on mailbox count and activate the on-prem console. Because it is a one-time fee rather than an annual subscription, it is usually the cheapest option for a single planned migration. | Near-zero - continuous sync, minutes to cut over | Agentless | Mid | Current | Delta / incremental passes; Wave / batch orchestration; Programme reporting / audit trail | Excellent value with a genuinely usable console, automatic mailbox matching, and strong public folder support. Runs on your own server so no mail data passes through a vendor cloud - which matters for data-residency reviews. | You supply and run the migration server and its bandwidth. Lighter on Teams/SharePoint than Quest or AvePoint. | https://www.codetwo.com/migration/
AvePoint Fly (Migration) | AvePoint | exchange |  | Paid | Per-user subscription, quote based | Per-user term subscription, usually bundled across mail, files and Teams. | Quote from AvePoint or a partner; also available through the Microsoft commercial marketplace. | Near-zero - continuous sync, minutes to cut over | Agentless | Enterprise | Current | Delta / incremental passes; Wave / batch orchestration; Coexistence during migration; Programme reporting / audit trail; Multi-tenant / multi-forest | Strongest when Teams, Groups, SharePoint and Power Platform matter as much as the mailbox - it preserves structure the mail-only tools drop. | No public pricing; sized for larger programmes. | https://www.avepoint.com/products/migration
ShareGate Migrate | ShareGate (Workleap) | exchange |  | Paid | Annual per-user or flat licence depending on plan | Annual subscription. | Buy online or via a partner; licence keyed to the desktop/server client. | Warm - seeded online, short cutover window | Agentless | Mid | Current | Wave / batch orchestration; Delta / incremental passes; Programme reporting / audit trail | The practitioner favourite for SharePoint, OneDrive and Teams content - use it alongside a mailbox tool rather than instead of one. | Not a mailbox migration tool. | https://sharegate.com/
SkyKick Migration Suites | SkyKick | exchange |  | Paid | Per-mailbox licence sold through MSP partners | Per-mailbox licence, sold almost entirely through the MSP/partner channel. | Purchase through a SkyKick partner or a distributor such as Pax8/Ingram. | Warm - seeded online, short cutover window | Agent | Smb | Current | Delta / incremental passes; Wave / batch orchestration; Workstation / device migration; Programme reporting / audit trail | Automates the whole SMB move including Outlook profile reconfiguration and DNS cutover planning - built for partners doing many small migrations. | SMB-oriented; partner-only purchase. | https://www.skykick.com/
Cloudiway | Cloudiway | exchange |  | Paid | Per-user licence, published online | Per-user licences bought online, plus separate coexistence subscriptions. | Self-service purchase on the Cloudiway site. | Near-zero - continuous sync, minutes to cut over | Agentless | Mid | Current | Delta / incremental passes; Coexistence during migration; Cross-org free/busy and GAL sync; Multi-tenant / multi-forest | Strong cross-platform coexistence (Google and Microsoft GAL sync, free/busy) at a lower price point than the big names. | Smaller support organisation. | https://cloudiway.com/
TransVault Migrator | TransVault | exchange |  | Paid | Per-mailbox or per-TB licence, quote based | Per-mailbox or capacity-based licensing, project oriented. | Quote from TransVault or a partner; frequently delivered as a managed service. | Warm - seeded online, short cutover window | Agent | Enterprise | Current | Delta / incremental passes; Programme reporting / audit trail; Chain-of-custody evidence | The specialist for legacy archives - Veritas Enterprise Vault, EMC SourceOne, Metalogix, Zantaz - into Microsoft 365, with chain-of-custody reporting for legal hold. | Archive-specific and expensive; you still need a mailbox tool for live data. | https://www.transvault.com/
Archive360 Archive2Azure | Archive360 | exchange |  | Paid | Capacity or per-user subscription | Subscription, capacity or user based. | Quote from Archive360. | Warm - seeded online, short cutover window | Agent | Enterprise | Current | Programme reporting / audit trail; Chain-of-custody evidence | Moves journal and compliance archives into a customer-controlled Azure tenancy with defensible reporting. | Compliance archive focus. | https://www.archive360.com/
Stellar Converter for EDB / Repair for Exchange | Stellar Information Technology | exchange |  | Paid | Per-technician annual licence | Annual technician licence. | Buy online from Stellar. | Cold - full outage for the whole copy | Agentless | Smb | Current |  | Extracts mailboxes straight out of an offline or damaged EDB into PST or Microsoft 365 - the rescue path when the source Exchange server will not start. | A recovery utility, not a migration platform. | https://www.stellarinfo.com/
Kernel Migrator for Exchange | Kernel (Lepide) | exchange |  | Paid | Per-mailbox or per-technician licence | Perpetual or annual licences by mailbox count or technician. | Buy online from Kernel/Lepide. | Warm - seeded online, short cutover window | Agentless | Mid | Current | Delta / incremental passes; Wave / batch orchestration; Programme reporting / audit trail | Low-cost mailbox and public folder migration with agentless operation. | Less proven at enterprise scale than Quest or BitTitan. | https://www.nucleustechnologies.com/
Microsoft Exchange Deployment Assistant / SARA | Microsoft | exchange, assessment |  | Free | No licence cost | Free Microsoft web tool and support diagnostic. | Use the web-based Deployment Assistant and download the Support and Recovery Assistant. Free. | Cold - full outage for the whole copy | Agentless | Enterprise | Current | Discovery and assessment; Programme reporting / audit trail | Generates a checklist tailored to your exact source version and target topology - the fastest way to a defensible plan. | Planning only. | https://learn.microsoft.com/exchange/