## Dashboard
NUCCT – Compliance Applicability & Readiness Assessment
Example Healthcare Corporation · Healthcare · September 20, 2026 · USA Cyber Security Compliance Check (NUCCT) by Niyyasoft
Assessment score | Maturity | Fully impl. | Partially impl. | Not impl. | Unknown | N/A | Critical gaps | High/critical risks | Months to close
64.9 | Developing | 18 | 22 | 3 | 1 | 0 | 9 | 20 | 9
Framework | Applicability | Score | Status | Controls | Gaps | Critical gaps
HIPAA Security Rule | Applicable | 68.1 | Developing | 33 | 17 | 7
HITECH Act | Applicable | 66.7 | Developing | 5 | 3 | 2
PCI DSS | Applicable | 64.5 | Developing | 39 | 23 | 8
State Data-Security Laws | Applicable | 73.5 | Developing | 25 | 10 | 6
NIST CSF 2.0 | Recommended Framework | 65.5 | Developing | 43 | 25 | 8
CISA CPGs | Recommended Framework | 64.3 | Developing | 31 | 18 | 6
Executive summary
The assessment identified 4 potentially applicable cybersecurity requirement sets: 4 assessed as applicable (HIPAA Security Rule, HITECH Act, PCI DSS and State Data-Security Laws). NIST CSF 2.0 and CISA CPGs are recommended as voluntary best-practice frameworks.
Across 44 controls in scope, the overall assessment score is 65% (Developing). 18 controls are fully implemented, 22 partially implemented and 3 not implemented; 1 is marked unknown and flagged for review.
The organization demonstrates established controls in awareness & training, backup & recovery, change management and continuous improvement. However, gaps remain in vulnerability scanning & management, multi-factor authentication (MFA), patch & flaw remediation, email & web security and least privilege & privileged access management (PAM).
26 gaps were identified, including 9 involving critical-priority controls and 20 rated high or critical risk. A phased remediation program of approximately 9 months (5 parallel workstreams) is estimated to close all gaps and complete independent validation.

## Applicability
Applicability analysis (rules engine)
Framework | Type | Applicability | In scope | Confidence | Why
HIPAA Security Rule | Regulatory requirement | Applicable | Yes | 75 | Company → Handles healthcare / protected health information: Yes → Industry: Healthcare → HIPAA Security Rule: Applicable — Healthcare organization handling PHI → likely a HIPAA covered entity (45 CFR 160.103); the Security Rule applies to ePHI. Company → Handles healthcare / protected health information: Yes → HIPAA Security Rule: Potentially Applicable — Handles health information → you may be a HIPAA business associate of a covered entity. Company → Industry: Healthcare → HIPAA Security Rule: Requires Review — Healthcare sector → confirm whether you are a covered entity or business associate.
HITECH Act | Regulatory requirement | Applicable | Yes | 55 | Company → Handles healthcare / protected health information: Yes → Industry: Healthcare → HITECH Act: Applicable — HIPAA covered entity → HITECH breach notification, tiered penalties and recognized-security-practice provisions apply. Company → Handles healthcare / protected health information: Yes → HITECH Act: Potentially Applicable — Handles health information → HITECH makes business associates directly liable for HIPAA compliance.
PCI DSS | Industry standard (non-government) | Applicable | Yes | 40 | Company → Processes, stores or transmits payment cards: Yes → PCI DSS: Applicable — Processes payment cards → PCI DSS is contractually required by the card brands through your acquiring bank. It is an industry standard, not a government regulation.
State Data-Security Laws | Regulatory requirement | Applicable | Yes | 50 | Company → Handles personally identifiable information (PII) of customers or employees: Yes → State Data-Security Laws: Applicable — Handles personal information → state breach-notification laws (all 50 states) and reasonable-security statutes (e.g., NY SHIELD Act, MA 201 CMR 17.00) apply based on where affected individuals live. Company → Country: United States → State Data-Security Laws: Potentially Applicable — U.S. business → virtually every organization holds employee or customer personal information subject to state breach laws.
NIST CSF 2.0 | Voluntary framework / standard | Recommended Framework | Yes | 40 | Company → Country: United States → NIST CSF 2.0: Recommended Framework — NIST CSF 2.0 is the recommended baseline framework for every U.S. organization. It is voluntary, but regulators, courts and insurers use it to judge "reasonable security". Company → Critical infrastructure organization: Yes → NIST CSF 2.0: Recommended Framework — Critical-infrastructure organization → federal policy promotes NIST CSF as the common risk language for critical infrastructure.
CISA CPGs | Voluntary framework / standard | Recommended Framework | Yes | 25 | Company → Critical infrastructure organization: Yes → CISA CPGs: Recommended Framework — Critical-infrastructure organization → CISA Cross-Sector Performance Goals are CISA's prioritized baseline (voluntary).
DOE C2M2 v2.1 | Voluntary framework / standard | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
NIST SP 800-53 Rev. 5 | Voluntary framework / standard | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
FISMA | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
NIST SP 800-171 Rev. 3 | Contractual requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
CMMC 2.0 | Contractual requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
FedRAMP | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
FBI CJIS Security Policy | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
FDA Medical Device Cybersecurity | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
GLBA | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
FTC Safeguards Rule | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
FFIEC / Banking Agencies | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
SEC Cyber Rules | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
SOX IT General Controls | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
NERC CIP | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
TSA Security Directives | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
FCC CPNI & Breach Rules | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
FERPA | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
NYDFS 23 NYCRR 500 | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
State Insurance Data Security Laws | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.
CCPA / CPRA | Regulatory requirement | Likely Not Applicable | No | 0 | No applicability rule matched the profile.

## Frameworks
Framework-by-framework assessment
Framework | Issuing organization | Type | Score | Status | Full | Partial | Not impl. | Unknown | N/A | Critical gaps
HIPAA Security Rule | HHS Office for Civil Rights (OCR) | Regulatory requirement | 68.1 | Developing | 16 | 14 | 3 | 0 | 0 | 7
HITECH Act | HHS Office for Civil Rights (OCR) | Regulatory requirement | 66.7 | Developing | 2 | 3 | 0 | 0 | 0 | 2
PCI DSS | PCI Security Standards Council (private industry body founded by the card brands) — NOT a government agency | Industry standard (non-government) | 64.5 | Developing | 16 | 19 | 3 | 1 | 0 | 8
State Data-Security Laws | State attorneys general and state legislatures (e.g., New York SHIELD Act, Massachusetts 201 CMR 17.00, Texas, Oregon and 50 state breach statutes) | Regulatory requirement | 73.5 | Developing | 15 | 8 | 2 | 0 | 0 | 6
NIST CSF 2.0 | National Institute of Standards and Technology (NIST) | Voluntary framework / standard | 65.5 | Developing | 18 | 21 | 3 | 1 | 0 | 8
CISA CPGs | Cybersecurity and Infrastructure Security Agency (CISA) | Voluntary framework / standard | 64.3 | Developing | 13 | 14 | 3 | 1 | 0 | 6

## Controls
All controls and responses
ID | Control | Category | Priority | Question | Status | Gap description / notes | Framework references | Evidence expected
GV-01 | Cybersecurity program & strategy | Governance | High | Does the organization maintain a documented, leadership-approved cybersecurity program and strategy aligned with business objectives and legal obligations? | Fully Implemented |  | NIST CSF 2.0: GV.OC-01, GV.RM-01 CISA CPGs: 1.B HIPAA Security Rule: §164.308(a)(1)(i) PCI DSS: 12.1.1 State Data-Security Laws: NY GBL §899-bb(2); MA 201 CMR 17.03(1) | Approved cybersecurity program charter and strategy Board or executive approval minutes Program budget and roadmap Annual program review record
GV-02 | Accountable security leader (CISO / Qualified Individual) | Governance | High | Is a qualified individual (CISO, Qualified Individual or CIP Senior Manager) formally designated and accountable for the cybersecurity program, with adequate authority and resources? | Fully Implemented |  | NIST CSF 2.0: GV.RR-02 CISA CPGs: 1.B HIPAA Security Rule: §164.308(a)(2) PCI DSS: 12.4.1 State Data-Security Laws: NY GBL §899-bb(2)(b)(ii)(A)(1); MA 201 CMR 17.03(2)(a) | Written designation of the CISO / Qualified Individual Job description and reporting line Resourcing plan or vCISO/MSSP contract
GV-03 | Board & executive oversight | Governance | High | Does the board of directors (or equivalent senior body) formally oversee cyber risk and receive a written cybersecurity report at least annually? | Partially Implemented | The board receives an annual update, but cyber oversight is not in any committee charter. | NIST CSF 2.0: GV.RR-01, GV.OV-01 | Board / committee charter with cyber oversight Annual written CISO report to the board Board minutes showing cyber discussions Quarterly cyber dashboard
GV-04 | Written security policies | Governance | High | Are written cybersecurity policies and procedures approved by management, communicated to workforce members and reviewed at least annually? | Fully Implemented |  | NIST CSF 2.0: GV.PO-01, GV.PO-02 HIPAA Security Rule: §164.316(a)–(b) PCI DSS: 12.1.1–12.1.2 State Data-Security Laws: MA 201 CMR 17.03(1) | Approved policy set with version history Workforce policy attestations Annual policy review log
GV-05 | Risk assessment & risk management | Risk Management | Critical | Is a formal, documented cybersecurity risk assessment performed at least annually (and after major changes), with a maintained risk register and approved treatment plans? | Partially Implemented | The HIPAA risk analysis was last completed 26 months ago and excludes cloud-hosted systems. | NIST CSF 2.0: GV.RM-02, ID.RA-01 – ID.RA-06 HIPAA Security Rule: §164.308(a)(1)(ii)(A)–(B) HITECH Act: HITECH §13412 recognized security practices (P.L. 116-321) PCI DSS: 12.3.1 (targeted risk analysis) State Data-Security Laws: NY GBL §899-bb(2)(b)(ii)(A)(2); MA 201 CMR 17.03(2)(b) | Risk assessment report (methodology, scope, results) Risk register with owners and treatment plans Risk acceptance approvals Evidence of annual repetition
GV-06 | Compliance obligations & scope | Governance | Medium | Have all legal, regulatory and contractual cybersecurity obligations been identified in a compliance register, and is the assessment/authorization boundary of regulated systems documented? | Partially Implemented | No consolidated register of state breach-notification obligations. | NIST CSF 2.0: GV.OC-03 PCI DSS: 12.5.2 (annual scope confirmation) State Data-Security Laws: Register of state breach-notification and data-security statutes | Compliance obligations register Scope / boundary document and diagrams Legal review record
GV-07 | Third-party & supply-chain risk management | Third-Party Risk | High | Are vendors and service providers with access to your systems or sensitive data risk-assessed before onboarding, bound by contractual security requirements (e.g., BAAs, DFARS flow-down), and monitored periodically? | Partially Implemented | BAAs are in place, but vendors are not risk-tiered or reassessed annually. | NIST CSF 2.0: GV.SC-01 – GV.SC-10 CISA CPGs: 1.G, 1.H, 1.I HIPAA Security Rule: §164.308(b)(1), §164.314(a) HITECH Act: HITECH §13401 (business associates directly liable) PCI DSS: 12.8.1–12.8.5, 12.9 State Data-Security Laws: NY GBL §899-bb(2)(b)(ii)(A)(5); MA 201 CMR 17.03(2)(f) | Vendor inventory with risk tiers Completed due-diligence questionnaires / SOC reports Contracts with security and breach-notice clauses (BAAs, DFARS flow-downs) Annual reassessment records
GV-08 | Personnel security | Personnel Security | Medium | Are personnel screened before being granted access to sensitive systems, and are onboarding, role changes and terminations handled through a documented security process? | Fully Implemented |  | NIST CSF 2.0: GV.RR-04 CISA CPGs: 2.D HIPAA Security Rule: §164.308(a)(3) PCI DSS: 12.7.1 State Data-Security Laws: MA 201 CMR 17.03(2)(e) | Background-check policy and records Signed acceptable-use and confidentiality agreements Joiner/mover/leaver tickets Monthly leaver access audit
GV-09 | System Security Plan (SSP) & POA&M | Compliance Documentation | Critical | Is a current System Security Plan maintained that describes the system boundary, environment and how each requirement is implemented, together with a Plan of Action & Milestones (POA&M) for open items? | Partially Implemented | Security documentation exists per system, but there is no consolidated security plan or tracked plan of action. | NIST CSF 2.0: GV.PO-01, ID.IM-01 | System Security Plan (current version) POA&M with owners and milestones Network and data-flow diagrams SSP review/approval record
ID-01 | Hardware, cloud & OT asset inventory | Asset Management | High | Is there an accurate, automatically updated inventory of all hardware, virtual, cloud and OT assets, with owners and criticality, reconciled at least monthly? | Partially Implemented | Medical IoT and cloud assets are not in the CMDB. | NIST CSF 2.0: ID.AM-01, ID.AM-05 CISA CPGs: 1.A HIPAA Security Rule: §164.310(d)(1) PCI DSS: 12.5.1 (inventory of system components) | Asset inventory / CMDB export Discovery tool coverage report Monthly reconciliation record
ID-02 | Software inventory & authorized software | Asset Management | Medium | Is there a software inventory, with only approved software permitted to run (allow-listing or approval process) and unsupported (end-of-life) software identified and removed? | Partially Implemented | No allow-listing on clinical workstations. | NIST CSF 2.0: ID.AM-02 CISA CPGs: 2.Q PCI DSS: 12.5.1, 6.3.2 (software inventory) | Software inventory report Software approval process records Allow-listing policy End-of-life software register
ID-03 | Sensitive data inventory, classification & data flows | Data Protection | High | Do you know where all sensitive data (CUI, ePHI, customer NPI, PII, BES Cyber System Information) is stored, processed and transmitted, with classification labels and current network and data-flow diagrams? | Partially Implemented | ePHI discovered on unmanaged file shares during the last audit. | NIST CSF 2.0: ID.AM-03, ID.AM-07 CISA CPGs: 2.P HIPAA Security Rule: §164.308(a)(1)(ii)(A) PCI DSS: 1.2.4 (data-flow diagrams), 3.2.1, 12.5.2 | Data classification policy Sensitive-data discovery results Data-flow and network diagrams
ID-04 | Vulnerability scanning & management | Vulnerability Management | Critical | Are all internal and internet-facing assets scanned for vulnerabilities at least monthly (authenticated scans), with findings prioritized (e.g., CISA KEV) and tracked to closure against defined SLAs? | Partially Implemented | External scans are monthly, but internal authenticated scanning covers only servers. | NIST CSF 2.0: ID.RA-01 CISA CPGs: 1.E, 2.W HIPAA Security Rule: §164.308(a)(8) PCI DSS: 11.3.1 (internal quarterly), 11.3.2 (external ASV quarterly) State Data-Security Laws: NY GBL §899-bb(2)(b)(ii)(B)(4) | Authenticated scan reports (last 3 months) Vulnerability SLA policy Remediation tracking / aging metrics External attack-surface report
ID-05 | Penetration testing & independent validation | Security Testing | High | Is independent penetration testing performed at least annually and after significant changes, and are control-effectiveness assessments performed by qualified independent parties? | Fully Implemented |  | NIST CSF 2.0: ID.IM-02 CISA CPGs: 1.F HIPAA Security Rule: §164.308(a)(8) PCI DSS: 11.4.1–11.4.5 (annual penetration testing) State Data-Security Laws: NY GBL §899-bb(2)(b)(ii)(B)(4) | Penetration test reports (external, internal, application) Retest confirmation Independent assessment / audit reports
ID-06 | Threat intelligence & information sharing | Threat Intelligence | Medium | Does the organization consume threat intelligence (CISA advisories, KEV, sector ISACs) and act on relevant alerts in a documented way? | Fully Implemented |  | NIST CSF 2.0: ID.RA-02, ID.RA-03 CISA CPGs: 3.A PCI DSS: 6.3.1 (identify vulnerabilities from industry sources) | ISAC membership / CISA alert subscriptions Advisory triage log Threat briefings to leadership
PR-01 | Multi-factor authentication (MFA) | Identity & Access | Critical | Is MFA enforced for all remote access, privileged accounts, email and cloud applications and access to sensitive data — preferably phishing-resistant MFA (FIDO2/passkeys, PIV/CAC)? | Partially Implemented | MFA is implemented for administrators but not for all remote users. | NIST CSF 2.0: PR.AA-03 CISA CPGs: 2.H HIPAA Security Rule: §164.312(d) PCI DSS: 8.4.1–8.4.3, 8.5.1 State Data-Security Laws: MA 201 CMR 17.04(1) | Conditional-access / MFA policy export MFA coverage report (users, admins, remote) Legacy-authentication disabled evidence FIDO2 / PIV enrollment for privileged users
PR-02 | Account lifecycle & unique identities | Identity & Access | High | Does every user have a unique account, with approved provisioning, access reviews at least annually, and access revoked within 24 hours of termination? | Fully Implemented |  | NIST CSF 2.0: PR.AA-01, PR.AA-05 CISA CPGs: 2.C, 2.D HIPAA Security Rule: §164.312(a)(2)(i), §164.308(a)(3)(ii)(C) PCI DSS: 8.2.1–8.2.6, 7.2.4 (access reviews every 6 months) State Data-Security Laws: MA 201 CMR 17.04(1)–(2) | Identity-provider user list (unique IDs) Provisioning/deprovisioning tickets Access-review campaign results Dormant-account report
PR-03 | Least privilege & privileged access management (PAM) | Identity & Access | Critical | Are administrative privileges minimized, using separate admin accounts, just-in-time elevation, credential vaulting and session recording for privileged access? | Partially Implemented | Domain administrators still use standing privileges; no PAM vault. | NIST CSF 2.0: PR.AA-05 CISA CPGs: 2.E HIPAA Security Rule: §164.308(a)(4) PCI DSS: 7.2.1–7.2.2, 8.6.1–8.6.3 State Data-Security Laws: MA 201 CMR 17.04(2) | Privileged account inventory PAM vault and rotation reports Session recordings sample Local admin rights removal evidence
PR-04 | Credential & password hygiene | Identity & Access | Medium | Are default passwords changed before deployment, long passwords (15+ characters per NIST SP 800-63B) enforced, compromised passwords blocked, and failed-login throttling and alerting configured? | Fully Implemented |  | NIST CSF 2.0: PR.AA-01 CISA CPGs: 2.A, 2.B, 2.G HIPAA Security Rule: §164.308(a)(5)(ii)(D) PCI DSS: 2.2.2, 8.3.4, 8.3.6 State Data-Security Laws: MA 201 CMR 17.04(1) | Password policy (NIST SP 800-63B aligned) Default-credential scan results Lockout/throttling configuration Password manager deployment
PR-05 | Security awareness training & phishing simulation | Awareness & Training | High | Do all workforce members complete security awareness training at onboarding and at least annually, including phishing/social-engineering simulations and role-based training for privileged users? | Fully Implemented |  | NIST CSF 2.0: PR.AT-01, PR.AT-02 CISA CPGs: 2.I, 2.J HIPAA Security Rule: §164.308(a)(5)(i) PCI DSS: 12.6.1–12.6.3 State Data-Security Laws: NY GBL §899-bb(2)(b)(ii)(A)(4); MA 201 CMR 17.03(2)(b) | Training completion report (≥95%) Phishing simulation results Role-based training records
PR-06 | Encryption of data at rest | Data Protection | High | Is sensitive data encrypted at rest on servers, databases, laptops, mobile devices, removable media and backups — using FIPS 140-validated cryptography where required (e.g., CUI)? | Fully Implemented |  | NIST CSF 2.0: PR.DS-01 CISA CPGs: 2.K, 2.L HIPAA Security Rule: §164.312(a)(2)(iv) HITECH Act: HITECH §13402(h) — encryption renders PHI "secured" (breach safe harbor) PCI DSS: 3.5.1 State Data-Security Laws: MA 201 CMR 17.04(5) | Full-disk encryption compliance report Database/storage encryption configuration Key-management procedures FIPS 140 validation certificates
PR-07 | Encryption in transit | Data Protection | High | Is all sensitive data encrypted in transit over internal and external networks (TLS 1.2+ with strong ciphers, encrypted email or secure file transfer where needed)? | Fully Implemented |  | NIST CSF 2.0: PR.DS-02 CISA CPGs: 2.K HIPAA Security Rule: §164.312(e)(1), §164.312(e)(2)(ii) HITECH Act: HITECH §13402(h) PCI DSS: 4.2.1 State Data-Security Laws: MA 201 CMR 17.04(3) | TLS configuration scan results Certificate inventory Secure email / SFTP configuration
PR-08 | Secure configuration baselines & hardening | Secure Configuration | High | Are hardened configuration baselines (CIS Benchmarks / DISA STIGs) defined and enforced for operating systems, network devices and cloud services, with drift detection and unnecessary ports/services disabled? | Partially Implemented | CIS baselines applied to servers only. | NIST CSF 2.0: PR.PS-01 CISA CPGs: 2.N, 2.O PCI DSS: 2.2.1–2.2.7 | Approved baselines (CIS / STIG) Configuration compliance scan report Approved deviations log
PR-09 | Change management | Change Management | Medium | Are changes to production systems requested, security-impact analyzed, approved, tested and documented through a formal change-management process? | Fully Implemented |  | NIST CSF 2.0: ID.RA-07, PR.PS-01 PCI DSS: 6.5.1–6.5.6 | Change-management procedure Sample of approved change tickets Unauthorized-change monitoring report
PR-10 | Patch & flaw remediation | Patch Management | Critical | Are security patches applied within risk-based timelines (e.g., CISA KEV and critical internet-facing flaws within 14 days, other critical within 30 days) across operating systems, applications, firmware and network devices? | Partially Implemented | Third-party application patching averages 45 days. | NIST CSF 2.0: PR.PS-02, ID.RA-01 CISA CPGs: 1.E HIPAA Security Rule: §164.308(a)(1)(ii)(B) PCI DSS: 6.3.3 (critical patches within one month) State Data-Security Laws: MA 201 CMR 17.04(6) | Patch SLA policy Patch compliance reports KEV remediation tracking Exception register
PR-11 | Endpoint detection & response (EDR) / anti-malware | Endpoint Security | Critical | Is a centrally managed EDR/anti-malware solution deployed on all endpoints and servers, with tamper protection, automatic updates and alerts monitored? | Fully Implemented |  | NIST CSF 2.0: DE.CM-09, PR.PS-05 HIPAA Security Rule: §164.308(a)(5)(ii)(B) PCI DSS: 5.2.1–5.3.5 State Data-Security Laws: MA 201 CMR 17.04(7) | EDR coverage vs. asset inventory Tamper-protection policy Alert-handling records
PR-12 | Email & web security | Email & Web Security | High | Is inbound email filtered for phishing and malware, SPF/DKIM/DMARC enforced (p=reject), internet-sourced Office macros blocked, and web traffic filtered for malicious sites? | Partially Implemented | DMARC is at p=none (monitoring only). | NIST CSF 2.0: PR.PS-05, DE.CM-01 CISA CPGs: 2.M, 2.N HIPAA Security Rule: §164.308(a)(5)(ii)(B) PCI DSS: 5.4.1 (anti-phishing) | Email security configuration DMARC record at p=reject Macro-blocking policy DNS/web filtering reports
PR-13 | Network segmentation & boundary protection | Network Security | High | Are networks segmented (users, servers, regulated enclaves, OT, guest) with deny-by-default firewall rules at the boundaries and no high-risk services (RDP, SMB, Telnet) exposed to the internet? | Partially Implemented | Clinical and corporate networks are not segmented; medical devices share VLANs with users. | NIST CSF 2.0: PR.IR-01 CISA CPGs: 2.F, 2.W, 2.X PCI DSS: 1.2–1.4 (network security controls, CDE segmentation) | Network segmentation diagram Firewall rule-base and annual review External exposure scan (no RDP/SMB)
PR-14 | Secure remote access & Zero Trust | Network Security | High | Is remote access provided only through managed, encrypted and monitored channels (ZTNA or VPN) with MFA, device-posture checks and session controls? | Partially Implemented | Legacy VPN without device posture checks. | NIST CSF 2.0: PR.AA-05, PR.IR-01 HIPAA Security Rule: §164.312(e)(1) PCI DSS: 8.4.3 (MFA for remote network access) | Remote-access architecture ZTNA/VPN MFA and posture policy Vendor remote-access procedure Remote session logs
PR-15 | Data loss prevention & secure disposal | Data Protection | Medium | Are controls in place to prevent unauthorized exfiltration of sensitive data (DLP), and is data and media securely disposed of (NIST SP 800-88) when no longer needed? | Not Implemented | No DLP on email or cloud storage. | NIST CSF 2.0: PR.DS-01, PR.DS-10, ID.AM-08 CISA CPGs: 2.V HIPAA Security Rule: §164.310(d)(2)(i)–(ii) PCI DSS: 3.2.1 (retention), 9.4.6–9.4.7 (media destruction) State Data-Security Laws: NY GBL §899-bb(2)(b)(ii)(C)(4) | DLP policies and incident reports Data-retention schedule Certificates of destruction (NIST SP 800-88)
PR-16 | Physical & environmental security | Physical Security | Medium | Is physical access to facilities, data centers and equipment rooms restricted to authorized personnel, logged, and are visitors escorted and monitored? | Fully Implemented |  | NIST CSF 2.0: PR.AA-06 HIPAA Security Rule: §164.310(a)(1), §164.310(b)–(c) PCI DSS: 9.2–9.3 State Data-Security Laws: NY GBL §899-bb(2)(b)(ii)(C)(3); MA 201 CMR 17.03(2)(g) | Badge access lists and reviews Visitor logs CCTV coverage of sensitive areas
PR-17 | Secure software development & application security | Application Security | Medium | Are internally developed and customized applications built with a secure SDLC (NIST SSDF SP 800-218), including code scanning, dependency/SBOM analysis, security testing and a public vulnerability-disclosure policy? | Unknown | Patient-portal development practices not yet reviewed. | NIST CSF 2.0: PR.PS-06 CISA CPGs: 4.B, 4.C PCI DSS: 6.2.1–6.2.4, 6.4.1–6.4.3 | Secure SDLC standard (NIST SSDF) SAST/SCA scan results in CI/CD SBOMs Vulnerability disclosure policy and security.txt
PR-18 | Mobile device & removable media control | Endpoint Security | Medium | Are mobile devices and removable media managed (MDM enrollment, encryption, remote wipe) and is the use of removable media and transient devices controlled? | Fully Implemented |  | NIST CSF 2.0: PR.PS-01, PR.DS-01 CISA CPGs: 2.V HIPAA Security Rule: §164.310(d)(1) State Data-Security Laws: MA 201 CMR 17.04(5) | MDM enrollment report USB storage restriction policy Transient-device scanning procedure
PR-19 | Cloud security posture | Cloud Security | Medium | Are cloud environments (IaaS, PaaS and SaaS) continuously assessed for misconfigurations, excessive permissions and exposed data, with the shared-responsibility model documented and FedRAMP-authorized services used for federal data? | Partially Implemented | No CSPM for the Azure tenant. | NIST CSF 2.0: PR.PS-01, ID.AM-04 PCI DSS: 12.5.2, 12.8 (cloud providers in scope) | CSPM/CNAPP findings report Cloud account inventory Shared-responsibility matrix FedRAMP authorization of services used for federal data
DE-01 | Centralized logging & secure log retention | Monitoring & Logging | Critical | Are security logs (identity, endpoint, network, cloud and applications) centrally collected in a SIEM, protected from tampering, time-synchronized and retained for the required period? | Partially Implemented | SIEM ingests firewall and AD logs only; cloud logs retained 30 days. | NIST CSF 2.0: DE.CM-01, DE.CM-03, PR.PS-04 CISA CPGs: 2.T, 2.U HIPAA Security Rule: §164.312(b), §164.308(a)(1)(ii)(D) PCI DSS: 10.2–10.5 (12-month retention) | SIEM log-source inventory Log retention configuration Log integrity controls NTP configuration
DE-02 | 24x7 security monitoring & alerting (SOC / MDR) | Monitoring & Logging | High | Are security alerts monitored and triaged 24x7 (internal SOC or Managed Detection & Response), with defined escalation and response times? | Not Implemented | Alerts are monitored during business hours only; no 24x7 SOC or MDR. | NIST CSF 2.0: DE.CM-01, DE.AE-02, DE.AE-03 CISA CPGs: 3.A HIPAA Security Rule: §164.308(a)(1)(ii)(D), §164.308(a)(5)(ii)(C) PCI DSS: 10.4.1, 11.5.1 (intrusion detection) State Data-Security Laws: NY GBL §899-bb(2)(b)(ii)(B)(3); MA 201 CMR 17.04(4) | SOC/MDR contract or staffing roster Detection use-case catalog MTTD/MTTR metrics Escalation matrix
RS-01 | Incident response plan | Incident Response | Critical | Is there a written, approved incident response plan defining roles, severity levels, communications, evidence handling, escalation to executives and decision authority? | Fully Implemented |  | NIST CSF 2.0: RS.MA-01, ID.IM-04 CISA CPGs: 2.S HIPAA Security Rule: §164.308(a)(6) PCI DSS: 12.10.1 State Data-Security Laws: NY GBL §899-bb(2)(b)(ii)(B)(3) | Approved incident response plan Scenario playbooks IR retainer and counsel contacts Out-of-band communications plan
RS-02 | Incident response testing & tabletop exercises | Incident Response | High | Are the incident response and continuity plans tested at least annually through tabletop or functional exercises involving executives, with lessons learned tracked? | Not Implemented | The incident response plan has not been exercised in over two years. | NIST CSF 2.0: ID.IM-02, ID.IM-04 CISA CPGs: 5.A HIPAA Security Rule: §164.308(a)(7)(ii)(D) PCI DSS: 12.10.2 (annual review & test) | Tabletop exercise agenda and attendance After-action report Plan-update tracking
RS-03 | Regulatory & contractual incident notification | Incident Response | Critical | Are notification procedures and templates in place to meet every applicable deadline — e.g., DoD/DIBNet 72 hours, NYDFS 72 hours, banking regulators 36 hours, SEC 8-K four business days after materiality, FTC 30 days (500+ consumers), HIPAA no later than 60 days, and state breach laws? | Partially Implemented | HIPAA notification procedure exists; card-brand and state notification steps are missing. | NIST CSF 2.0: RS.CO-02, RS.CO-03 CISA CPGs: 4.A HIPAA Security Rule: §164.400–414 (Breach Notification Rule) HITECH Act: HITECH §13402 (notification to individuals, HHS and media) PCI DSS: 12.10.1 (notify acquirer and card brands) State Data-Security Laws: State breach-notification statutes (all 50 states) | Regulatory notification matrix Notification templates DoD medium-assurance certificate (if DIBNet reporting applies)
RS-04 | Incident analysis, forensics & containment | Incident Response | Medium | Can the organization rapidly analyze, contain and eradicate incidents, preserving forensic evidence (e.g., images retained for 90 days under DFARS 7012)? | Partially Implemented | No forensic retainer. | NIST CSF 2.0: RS.AN-03, RS.MI-01, RS.MI-02 HIPAA Security Rule: §164.308(a)(6)(ii) PCI DSS: 12.10.1 | Containment procedures EDR isolation capability Chain-of-custody forms Evidence-retention rules
RC-01 | Secure, immutable & tested backups | Backup & Recovery | Critical | Are critical systems and data backed up following the 3-2-1 rule, with at least one immutable or offline copy, encrypted, isolated from production credentials, and restores tested at least quarterly? | Fully Implemented |  | NIST CSF 2.0: PR.DS-11, RC.RP-03 CISA CPGs: 2.R HIPAA Security Rule: §164.308(a)(7)(ii)(A) | Backup policy with RTO/RPO Immutable/offline copy configuration Quarterly restore test results Separate backup admin credentials with MFA
RC-02 | Business continuity & disaster recovery | Disaster Recovery & Continuity | High | Are business continuity and disaster recovery plans documented from a business impact analysis, with defined RTO/RPO, and tested at least annually? | Partially Implemented | The DR plan exists, but the EHR failover has never been tested. | NIST CSF 2.0: RC.RP-01 – RC.RP-06 CISA CPGs: 5.A HIPAA Security Rule: §164.308(a)(7)(i), §164.308(a)(7)(ii)(B)–(E) | Business impact analysis BC/DR plans Annual DR test report Alternate-site agreements
RC-03 | Lessons learned & continuous improvement | Continuous Improvement | Medium | After incidents, exercises and assessments, are lessons learned documented and the program (plans, controls, training) updated and tracked to closure? | Fully Implemented |  | NIST CSF 2.0: ID.IM-03, RC.CO-03 HIPAA Security Rule: §164.308(a)(8) PCI DSS: 12.10.6 State Data-Security Laws: NY GBL §899-bb(2)(b)(ii)(A)(6) | Post-incident review reports Improvement backlog Annual program evaluation
GV-21 | PCI DSS scope reduction & annual validation | Regulatory Reporting & Certification | Critical | Is the cardholder data environment scoped and minimized (tokenization / P2PE / outsourced payment pages), sensitive authentication data never stored after authorization, and PCI DSS compliance validated annually (ROC or SAQ with AOC) with quarterly ASV scans? | Partially Implemented | SAQ D completed; tokenization not yet deployed for the patient-payment portal. | PCI DSS: 12.5.2, 3.3.1, 11.3.2; ROC/SAQ and AOC | Attestation of Compliance (AOC) ROC or SAQ Quarterly ASV scan reports Scope confirmation

## Gap Action Plan
Remediation action plan
ID | Risk | Phase | Control | Status | Owner | Gap | Recommended remediation | Technology | Target date | Progress | Comments
ID-04 | Critical | 1 | Vulnerability scanning & management | Partially Implemented | CISO | External scans are monthly, but internal authenticated scanning covers only servers. | • Deploy authenticated internal and external scanning • Enroll in free CISA Cyber Hygiene scanning for external exposure • Define remediation SLAs (KEV within 2 weeks for internet-facing systems) • Report aging and SLA metrics monthly | Vulnerability & Exposure Management | 2026-10-18 | Not started
PR-01 | Critical | 1 | Multi-factor authentication (MFA) | Partially Implemented | CISO / CIO | MFA is implemented for administrators but not for all remote users. | • Enable MFA for administrators and remote access first • Extend to all users on email and SaaS through conditional access • Disable legacy/basic authentication protocols • Migrate privileged users to phishing-resistant FIDO2 keys | Identity & Access Management (SSO / MFA / Conditional Access) | 2026-10-18 | Not started
PR-10 | Critical | 1 | Patch & flaw remediation | Partially Implemented | CIO | Third-party application patching averages 45 days. | • Define patch SLAs by severity and exposure • Automate OS and third-party patching • Include network devices and firmware in patch cycles • Report patch compliance weekly and track exceptions | Unified Endpoint, Patch & Configuration Management Vulnerability & Exposure Management | 2026-10-25 | Not started
PR-12 | Critical | 1 | Email & web security | Partially Implemented | CIO | DMARC is at p=none (monitoring only). | • Deploy advanced email filtering with sandboxing • Move DMARC from monitoring to p=reject • Block internet-sourced macros by policy • Implement DNS/web filtering for all users | Email Security & DMARC Enforcement Zero Trust Access / Security Service Edge (ZTNA, SWG, CASB) | 2026-10-18 | Not started
PR-03 | Critical | 1 | Least privilege & privileged access management (PAM) | Partially Implemented | CISO | Domain administrators still use standing privileges; no PAM vault. | • Inventory all privileged and service accounts • Separate admin accounts from daily-use accounts • Deploy a PAM vault with rotation and session recording • Remove local admin rights and implement just-in-time elevation | Privileged Access Management (PAM) | 2026-11-01 | Not started
PR-14 | Critical | 2 | Secure remote access & Zero Trust | Partially Implemented | CTO | Legacy VPN without device posture checks. | • Inventory all remote-access paths, including vendor access • Consolidate onto ZTNA or a hardened VPN with MFA • Enforce device-posture checks • Log and review remote sessions | Zero Trust Access / Security Service Edge (ZTNA, SWG, CASB) Identity & Access Management (SSO / MFA / Conditional Access) | 2026-12-20 | Not started
DE-02 | Critical | 2 | 24x7 security monitoring & alerting (SOC / MDR) | Not Implemented | CISO | Alerts are monitored during business hours only; no 24x7 SOC or MDR. | • Decide between an internal SOC and an MDR provider • Define detection use cases and escalation paths • Integrate EDR, identity and cloud alerts • Track detection and response metrics monthly | Managed Detection & Response (24x7 SOC) Security Information & Event Management (SIEM) | 2027-01-10 | Not started
PR-13 | Critical | 2 | Network segmentation & boundary protection | Partially Implemented | CTO | Clinical and corporate networks are not segmented; medical devices share VLANs with users. | • Close internet-exposed high-risk services immediately • Design security zones and a segmentation model • Implement deny-by-default rules between zones • Review firewall rules at least annually | Next-Generation Firewalls & Network Segmentation Network Access Control (NAC) | 2027-01-03 | Not started
PR-19 | High | 3 | Cloud security posture | Partially Implemented | CTO | No CSPM for the Azure tenant. | • Inventory all cloud accounts and SaaS tenants • Deploy CSPM/CNAPP with benchmark policies • Remediate public exposure and excessive permissions • Use FedRAMP Moderate (or equivalent) services for CUI/federal data | Cloud Security Posture / Cloud-Native Application Protection (CSPM / CNAPP) | 2027-02-14 | Not started
GV-05 | High | 1 | Risk assessment & risk management | Partially Implemented | CISO / CRO | The HIPAA risk analysis was last completed 26 months ago and excludes cloud-hosted systems. | • Adopt a risk methodology (NIST SP 800-30 / CSF GV.RM) • Inventory in-scope systems and data, then rate threats and vulnerabilities • Build a risk register with owners, treatment decisions and due dates • Present results to executives; repeat annually and upon major change | Governance, Risk & Compliance (GRC) Automation | 2026-11-08 | Not started
GV-09 | High | 1 | System Security Plan (SSP) & POA&M | Partially Implemented | CISO | Security documentation exists per system, but there is no consolidated security plan or tracked plan of action. | • Define the authorization/assessment boundary and diagrams • Write implementation statements for each requirement • Record every gap in a POA&M with owners and dates • Review the SSP annually and after significant change | Governance, Risk & Compliance (GRC) Automation | 2026-11-15 | Not started
DE-01 | High | 1 | Centralized logging & secure log retention | Partially Implemented | CISO | SIEM ingests firewall and AD logs only; cloud logs retained 30 days. | • Define required log sources and retention periods • Deploy or expand the SIEM and onboard priority sources • Protect logs from alteration and synchronize time • Monitor log-source health and gaps | Security Information & Event Management (SIEM) | 2026-11-15 | Not started
GV-21 | High | 1 | PCI DSS scope reduction & annual validation | Partially Implemented | CFO / CISO | SAQ D completed; tokenization not yet deployed for the patient-payment portal. | • Map card-data flows and confirm scope • Reduce scope with tokenization, P2PE or hosted payment pages • Remediate PCI DSS v4.0.1 requirements • Validate annually (ROC/SAQ) and run quarterly ASV scans | Payment Data Security (Tokenization / P2PE / Hosted Payments) Vulnerability & Exposure Management | 2026-11-29 | Not started
RS-02 | High | 1 | Incident response testing & tabletop exercises | Not Implemented | CISO | The incident response plan has not been exercised in over two years. | • Schedule an annual executive tabletop (use CISA Tabletop Exercise Packages) • Run technical exercises for the IT/SOC teams • Document after-action reports • Track plan improvements to closure | Incident Response Retainer & Forensics | 2026-11-15 | Not started
ID-01 | High | 2 | Hardware, cloud & OT asset inventory | Partially Implemented | CIO | Medical IoT and cloud assets are not in the CMDB. | • Deploy automated discovery across network, endpoint and cloud • Consolidate into one authoritative inventory (CMDB) • Assign owners and criticality to each asset • Reconcile monthly and alert on unknown devices | Asset Inventory & CMDB (Cyber Asset Attack Surface Management) | 2026-12-20 | Not started
GV-07 | High | 2 | Third-party & supply-chain risk management | Partially Implemented | CPO / CISO | BAAs are in place, but vendors are not risk-tiered or reassessed annually. | • Build a complete vendor inventory and tier vendors by data access and criticality • Standardize due-diligence questionnaires and contract security clauses • Execute BAAs / DFARS 7012 flow-downs where required • Monitor critical vendors continuously and reassess annually | Third-Party Risk Management & Security Ratings Governance, Risk & Compliance (GRC) Automation | 2026-12-27 | Not started
ID-03 | High | 2 | Sensitive data inventory, classification & data flows | Partially Implemented | CIO / CDO | ePHI discovered on unmanaged file shares during the last audit. | • Define a data classification policy and labels • Run automated data discovery across file shares, SaaS and cloud • Document network topology and data-flow diagrams • Minimize and consolidate regulated data into protected enclaves | Data Discovery, Classification & Loss Prevention | 2027-01-17 | Not started
PR-15 | High | 3 | Data loss prevention & secure disposal | Not Implemented | CISO | No DLP on email or cloud storage. | • Define a data-retention and disposal schedule • Deploy DLP in monitor mode, then enforce on regulated data • Block unauthorized USB and personal cloud storage • Use certified NIST SP 800-88 sanitization with certificates | Data Discovery, Classification & Loss Prevention | 2027-03-07 | Not started
PR-08 | High | 2 | Secure configuration baselines & hardening | Partially Implemented | CTO | CIS baselines applied to servers only. | • Adopt CIS Benchmarks or DISA STIGs per platform • Enforce baselines through management tooling • Scan for configuration compliance and drift • Document approved deviations | Unified Endpoint, Patch & Configuration Management Cloud Security Posture / Cloud-Native Application Protection (CSPM / CNAPP) | 2027-01-17 | Not started
PR-17 | High | 3 | Secure software development & application security | Unknown | CTO | Patient-portal development practices not yet reviewed. | • Adopt NIST SSDF practices and secure coding standards • Integrate SAST, SCA and secrets scanning into CI/CD • Generate SBOMs and monitor dependencies • Publish a vulnerability-disclosure policy and security.txt | Application Security Testing & Software Supply Chain Web Application Firewall & DDoS Protection | 2027-03-21 | Not started
RS-03 | Medium | 1 | Regulatory & contractual incident notification | Partially Implemented | General Counsel | HIPAA notification procedure exists; card-brand and state notification steps are missing. | • Build a notification matrix covering federal, state and contractual obligations • Prepare templates and approval workflows • Obtain prerequisites (e.g., DoD medium-assurance certificate) • Embed deadlines in the IR plan and exercise them | Incident Response Retainer & Forensics | 2026-11-22 | Not started
RC-02 | Medium | 2 | Business continuity & disaster recovery | Partially Implemented | COO / CIO | The DR plan exists, but the EHR failover has never been tested. | • Perform a business impact analysis • Document BC/DR plans with RTO/RPO per system • Establish alternate processing capability • Test annually and remediate findings | Immutable Backup & Cyber Recovery | 2027-01-24 | Not started
RS-04 | Medium | 3 | Incident analysis, forensics & containment | Partially Implemented | CISO | No forensic retainer. | • Define containment and eradication procedures • Ensure remote isolation capability through EDR • Retain an IR firm with forensic capability • Document chain-of-custody and evidence-retention rules | Incident Response Retainer & Forensics Endpoint Detection & Response (EDR / XDR) | 2027-02-14 | Not started
ID-02 | Medium | 3 | Software inventory & authorized software | Partially Implemented | CIO | No allow-listing on clinical workstations. | • Collect software inventory from endpoint agents • Establish a software approval process • Enforce allow-listing on servers and high-risk endpoints • Retire or isolate end-of-life software | Asset Inventory & CMDB (Cyber Asset Attack Surface Management) Unified Endpoint, Patch & Configuration Management | 2027-02-14 | Not started
GV-03 | Medium | 1 | Board & executive oversight | Partially Implemented | CEO / Board | The board receives an annual update, but cyber oversight is not in any committee charter. | • Assign cyber oversight to the board or a committee in its charter • Establish a quarterly cyber dashboard and an annual written report • Provide directors with cyber-risk briefings or training • Record oversight activities in board minutes | Governance, Risk & Compliance (GRC) Automation | 2026-11-29 | Not started
GV-06 | Medium | 3 | Compliance obligations & scope | Partially Implemented | General Counsel / CISO | No consolidated register of state breach-notification obligations. | • Inventory contracts, regulations and state laws that apply • Create a compliance register mapped to controls and owners • Define and document the regulated system boundary (e.g., CUI enclave) • Review the register quarterly with Legal | Governance, Risk & Compliance (GRC) Automation | 2027-02-28 | Not started

## Risk Register
Risk register
ID | Risk area | What can happen | L | I | Score | Rating | Risk factors | Owner | Treatment
ID-04 | Vulnerability scanning & management | Known, exploitable vulnerabilities remain open; exploitation of public-facing weaknesses is a leading cause of breaches. | 5 | 5 | 25 | Critical | Control importance: Critical Exposure: remote workforce, public cloud, SaaS, hybrid cloud Regulatory relevance: HIPAA Security Rule, PCI DSS, State Data-Security Laws | CISO | Mitigate
PR-01 | Multi-factor authentication (MFA) | Stolen or phished passwords lead directly to account takeover, business email compromise and ransomware. | 5 | 5 | 25 | Critical | Control importance: Critical Exposure: remote workforce, public cloud, SaaS, hybrid cloud Data sensitivity: PHI, cardholder data Regulatory relevance: HIPAA Security Rule, PCI DSS, State Data-Security Laws | CISO / CIO | Mitigate
PR-10 | Patch & flaw remediation | Unpatched known-exploited vulnerabilities are among the most common ransomware entry points. | 5 | 5 | 25 | Critical | Control importance: Critical Exposure: remote workforce, public cloud, SaaS, hybrid cloud Regulatory relevance: HIPAA Security Rule, PCI DSS, State Data-Security Laws | CIO | Mitigate
PR-12 | Email & web security | Phishing and business email compromise cause the largest reported cybercrime losses in the U.S. (FBI IC3). | 5 | 5 | 25 | Critical | Control importance: High Exposure: remote workforce, public cloud, SaaS, hybrid cloud Regulatory relevance: HIPAA Security Rule, PCI DSS | CIO | Mitigate
PR-03 | Least privilege & privileged access management (PAM) | Compromise of a single over-privileged account enables domain-wide ransomware deployment. | 4 | 5 | 20 | Critical | Control importance: Critical Exposure: remote workforce, public cloud, SaaS, hybrid cloud Data sensitivity: PHI, cardholder data Regulatory relevance: HIPAA Security Rule, PCI DSS, State Data-Security Laws | CISO | Mitigate
PR-14 | Secure remote access & Zero Trust | Compromised VPN credentials and exposed remote-access services are a top initial-access vector. | 4 | 5 | 20 | Critical | Control importance: High Exposure: remote workforce, public cloud, SaaS, hybrid cloud Business criticality: critical infrastructure Regulatory relevance: HIPAA Security Rule, PCI DSS | CTO | Mitigate
DE-02 | 24x7 security monitoring & alerting (SOC / MDR) | Attacks launched at night or on weekends proceed unchallenged; average dwell time increases dramatically. | 4 | 5 | 20 | Critical | Control importance: High Data sensitivity: PHI, cardholder data Regulatory relevance: HIPAA Security Rule, PCI DSS, State Data-Security Laws | CISO | Mitigate
PR-13 | Network segmentation & boundary protection | Flat networks allow a single compromised device to reach every system, including backups and OT. | 4 | 5 | 20 | Critical | Control importance: High Exposure: remote workforce, public cloud, SaaS, hybrid cloud Business criticality: critical infrastructure Regulatory relevance: PCI DSS | CTO | Mitigate
PR-19 | Cloud security posture | Misconfigured cloud storage and over-privileged cloud identities expose data publicly. | 4 | 4 | 16 | High | Control importance: Medium Exposure: remote workforce, public cloud, SaaS, hybrid cloud Regulatory relevance: PCI DSS | CTO | Mitigate
GV-05 | Risk assessment & risk management | Resources are spent on the wrong problems; missing risk analysis is the single most cited violation in HIPAA and FTC enforcement. | 3 | 5 | 15 | High | Control importance: Critical Regulatory relevance: HIPAA Security Rule, HITECH Act, PCI DSS, State Data-Security Laws | CISO / CRO | Mitigate
GV-09 | System Security Plan (SSP) & POA&M | Without an SSP an assessment cannot be passed (CMMC, FedRAMP) and any SPRS score is unsupported, creating False Claims Act exposure. | 3 | 5 | 15 | High | Control importance: Critical | CISO | Mitigate
DE-01 | Centralized logging & secure log retention | Without logs, incidents go unnoticed and investigations cannot establish scope, forcing worst-case breach notifications. | 3 | 5 | 15 | High | Control importance: Critical Data sensitivity: PHI, cardholder data Regulatory relevance: HIPAA Security Rule, PCI DSS | CISO | Mitigate
GV-21 | PCI DSS scope reduction & annual validation | Card-brand fines passed through by the acquirer, increased transaction fees, liability for fraud losses and possible loss of the ability to accept cards. | 3 | 5 | 15 | High | Control importance: Critical Regulatory relevance: PCI DSS | CFO / CISO | Mitigate
RS-02 | Incident response testing & tabletop exercises | Untested plans fail under pressure; executives are unprepared for critical decisions such as ransom and disclosure. | 3 | 5 | 15 | High | Control importance: High Data sensitivity: PHI, cardholder data Business criticality: critical infrastructure Regulatory relevance: HIPAA Security Rule, PCI DSS | CISO | Mitigate
ID-01 | Hardware, cloud & OT asset inventory | You cannot protect what you do not know; unmanaged assets are a primary entry point for attackers. | 3 | 5 | 15 | High | Control importance: High Regulatory relevance: HIPAA Security Rule, PCI DSS | CIO | Mitigate
GV-07 | Third-party & supply-chain risk management | A compromised vendor becomes your breach (as in the MOVEit, SolarWinds and Change Healthcare incidents), and you remain accountable to regulators. | 3 | 5 | 15 | High | Control importance: High Data sensitivity: PHI, cardholder data Regulatory relevance: HIPAA Security Rule, HITECH Act, PCI DSS, State Data-Security Laws | CPO / CISO | Mitigate
ID-03 | Sensitive data inventory, classification & data flows | Regulated data sprawls to unprotected locations, expanding breach impact and notification obligations. | 3 | 5 | 15 | High | Control importance: High Data sensitivity: PHI, cardholder data Regulatory relevance: HIPAA Security Rule, PCI DSS | CIO / CDO | Mitigate
PR-15 | Data loss prevention & secure disposal | Sensitive data leaves the organization unnoticed, or is recovered from discarded equipment. | 3 | 5 | 15 | High | Control importance: Medium Data sensitivity: PHI, cardholder data Regulatory relevance: HIPAA Security Rule, PCI DSS, State Data-Security Laws | CISO | Mitigate
PR-08 | Secure configuration baselines & hardening | Insecure defaults and configuration drift create easy footholds and lateral-movement paths. | 3 | 4 | 12 | High | Control importance: High Regulatory relevance: PCI DSS | CTO | Mitigate
PR-17 | Secure software development & application security | Application flaws expose customer data and the organization's own software supply chain. | 3 | 4 | 12 | High | Control importance: Medium Regulatory relevance: PCI DSS Status unknown — flagged for review | CTO | Mitigate
RS-03 | Regulatory & contractual incident notification | Missed notification deadlines convert an incident into a separate regulatory violation with penalties. | 2 | 5 | 10 | Medium | Control importance: Critical Data sensitivity: PHI, cardholder data Business criticality: critical infrastructure Regulatory relevance: HIPAA Security Rule, HITECH Act, PCI DSS, State Data-Security Laws | General Counsel | Mitigate
RC-02 | Business continuity & disaster recovery | Extended outages after a cyberattack or disaster cause revenue loss, contractual penalties and customer attrition. | 2 | 5 | 10 | Medium | Control importance: High Business criticality: critical infrastructure Regulatory relevance: HIPAA Security Rule | COO / CIO | Mitigate
RS-04 | Incident analysis, forensics & containment | Incomplete eradication leads to re-infection, and lost evidence undermines legal and insurance positions. | 2 | 5 | 10 | Medium | Control importance: Medium Data sensitivity: PHI, cardholder data Business criticality: critical infrastructure Regulatory relevance: HIPAA Security Rule, PCI DSS | CISO | Mitigate
ID-02 | Software inventory & authorized software | Unauthorized and unsupported software introduces exploitable vulnerabilities and license risk. | 3 | 3 | 9 | Medium | Control importance: Medium Regulatory relevance: PCI DSS | CIO | Mitigate
GV-03 | Board & executive oversight | Directors cannot demonstrate oversight, increasing personal liability and disclosure risk; material risks go unnoticed. | 2 | 4 | 8 | Medium | Control importance: High | CEO / Board | Mitigate
GV-06 | Compliance obligations & scope | Unknown obligations are missed entirely, and an undefined scope forces costly controls everywhere or leaves regulated data unprotected. | 2 | 4 | 8 | Medium | Control importance: Medium Regulatory relevance: PCI DSS, State Data-Security Laws | General Counsel / CISO | Mitigate

## Time Plan
Time plan – remediation roadmap
38 weeks (about 9 months) · Sep 20, 2026 – Jun 13, 2027 · 5 parallel workstreams
Workstream | Owner | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | Weeks | Target
Phase 0 — Mobilize & Govern | [10 empty] | 2 | 2026-10-04
Phase 1 — Stabilize & Protect | [10 empty] | 8 | 2026-11-29
ID-04 Vulnerability scanning & management | CISO | [9 empty] | 2 | 2026-10-18
PR-01 Multi-factor authentication (MFA) | CISO / CIO | [9 empty] | 2 | 2026-10-18
PR-10 Patch & flaw remediation | CIO | [9 empty] | 3 | 2026-10-25
PR-12 Email & web security | CIO | [9 empty] | 2 | 2026-10-18
PR-03 Least privilege & privileged access management (PAM) | CISO | [9 empty] | 4 | 2026-11-01
GV-05 Risk assessment & risk management | CISO / CRO | [9 empty] | 3 | 2026-11-08
GV-09 System Security Plan (SSP) & POA&M | CISO | [9 empty] | 4 | 2026-11-15
DE-01 Centralized logging & secure log retention | CISO | [9 empty] | 4 | 2026-11-15
GV-21 PCI DSS scope reduction & annual validation | CFO / CISO | [9 empty] | 5 | 2026-11-29
RS-02 Incident response testing & tabletop exercises | CISO | [9 empty] | 2 | 2026-11-15
RS-03 Regulatory & contractual incident notification | General Counsel | [9 empty] | 2 | 2026-11-22
GV-03 Board & executive oversight | CEO / Board | [9 empty] | 2 | 2026-11-29
Phase 2 — Build the Foundation | [10 empty] | 8 | 2027-01-24
PR-14 Secure remote access & Zero Trust | CTO | [9 empty] | 3 | 2026-12-20
DE-02 24x7 security monitoring & alerting (SOC / MDR) | CISO | [9 empty] | 6 | 2027-01-10
PR-13 Network segmentation & boundary protection | CTO | [9 empty] | 5 | 2027-01-03
ID-01 Hardware, cloud & OT asset inventory | CIO | [9 empty] | 3 | 2026-12-20
GV-07 Third-party & supply-chain risk management | CPO / CISO | [9 empty] | 4 | 2026-12-27
ID-03 Sensitive data inventory, classification & data flows | CIO / CDO | [9 empty] | 4 | 2027-01-17
PR-08 Secure configuration baselines & hardening | CTO | [9 empty] | 4 | 2027-01-17
RC-02 Business continuity & disaster recovery | COO / CIO | [9 empty] | 4 | 2027-01-24
Phase 3 — Mature & Optimize | [10 empty] | 8 | 2027-03-21
PR-19 Cloud security posture | CTO | [9 empty] | 3 | 2027-02-14
PR-15 Data loss prevention & secure disposal | CISO | [9 empty] | 6 | 2027-03-07
PR-17 Secure software development & application security | CTO | [9 empty] | 8 | 2027-03-21
RS-04 Incident analysis, forensics & containment | CISO | [9 empty] | 3 | 2027-02-14
ID-02 Software inventory & authorized software | CIO | [9 empty] | 3 | 2027-02-14
GV-06 Compliance obligations & scope | General Counsel / CISO | [9 empty] | 2 | 2027-02-28
Phase 4 — Validate & Sustain | [10 empty] | 12 | 2027-06-13
Phase | Goal
Phase 0 — Mobilize & Govern | Establish sponsorship, governance, budget and a program office so remediation starts with authority.
Phase 1 — Stabilize & Protect | Close critical gaps and quick wins most likely to cause a breach or a regulatory violation.
Phase 2 — Build the Foundation | Implement core architecture and processes required by the in-scope frameworks.
Phase 3 — Mature & Optimize | Complete remaining requirements, automate evidence collection and raise maturity.
Phase 4 — Validate & Sustain | Independently validate control implementation, complete required attestations and move to continuous monitoring.

## Technology (US OEMs)
Technology to close the gaps — American OEMs
Technology category | What it does | Urgency | Gaps | Gaps closed | OEM / vendor | Example product | U.S. headquarters
Vulnerability & Exposure Management | Authenticated scanning, external attack-surface management and risk-based prioritization (KEV / EPSS). | Immediate (Phase 1) | 3 | ID-04 Vulnerability scanning & management PR-10 Patch & flaw remediation GV-21 PCI DSS scope reduction & annual validation | Tenable | Tenable One / Nessus | Columbia, MD
[5 empty] | Rapid7 | InsightVM | Boston, MA
[5 empty] | Qualys | VMDR | Foster City, CA
Unified Endpoint, Patch & Configuration Management | Enforces hardened baselines, automates OS and third-party patching, encryption and mobile-device management. | Immediate (Phase 1) | 3 | PR-10 Patch & flaw remediation PR-08 Secure configuration baselines & hardening ID-02 Software inventory & authorized software | Microsoft | Intune / Configuration Manager | Redmond, WA
[5 empty] | Tanium | Tanium Patch & Configuration | Kirkland, WA
[5 empty] | Jamf | Jamf Pro (Apple devices) | Minneapolis, MN
[5 empty] | Ivanti | Neurons for Patch Management | South Jordan, UT
Identity & Access Management (SSO / MFA / Conditional Access) | Central identity provider with single sign-on, phishing-resistant MFA, conditional access and automated lifecycle management. | Immediate (Phase 1) | 2 | PR-01 Multi-factor authentication (MFA) PR-14 Secure remote access & Zero Trust | Microsoft | Entra ID (Azure AD) P1/P2 | Redmond, WA
[5 empty] | Okta | Workforce Identity Cloud | San Francisco, CA
[5 empty] | Cisco | Duo | San Jose, CA
[5 empty] | Ping Identity | PingOne | Denver, CO
Zero Trust Access / Security Service Edge (ZTNA, SWG, CASB) | Replaces or hardens VPN with identity- and posture-aware access, secure web gateway and SaaS controls. | Immediate (Phase 1) | 2 | PR-12 Email & web security PR-14 Secure remote access & Zero Trust | Zscaler | Zero Trust Exchange (ZIA / ZPA) | San Jose, CA
[5 empty] | Netskope | Netskope One SSE | Santa Clara, CA
[5 empty] | Cloudflare | Cloudflare One | San Francisco, CA
[5 empty] | Palo Alto Networks | Prisma Access | Santa Clara, CA
[5 empty] | Fortinet | FortiSASE | Sunnyvale, CA
[5 empty] | Cisco | Secure Access | San Jose, CA
Email Security & DMARC Enforcement | Advanced phishing and malware protection, business-email-compromise detection and DMARC enforcement. | Immediate (Phase 1) | 1 | PR-12 Email & web security | Proofpoint | Email Protection | Sunnyvale, CA
[5 empty] | Microsoft | Defender for Office 365 | Redmond, WA
[5 empty] | Abnormal Security | Abnormal Human Behavior Security | San Francisco, CA
[5 empty] | Valimail | Valimail Enforce (DMARC) | San Francisco, CA
Security Information & Event Management (SIEM) | Centralized, tamper-resistant log collection, correlation, detection rules and long-term retention. | Immediate (Phase 1) | 2 | DE-02 24x7 security monitoring & alerting (SOC / MDR) DE-01 Centralized logging & secure log retention | Splunk (Cisco) | Splunk Enterprise Security | San Francisco, CA
[5 empty] | Microsoft | Sentinel | Redmond, WA
[5 empty] | Google | Google Security Operations | Mountain View, CA
[5 empty] | Rapid7 | InsightIDR | Boston, MA
[5 empty] | Fortinet | FortiSIEM | Sunnyvale, CA
Privileged Access Management (PAM) | Vaulting and rotation of privileged credentials, just-in-time elevation, session recording and endpoint least privilege. | Immediate (Phase 1) | 1 | PR-03 Least privilege & privileged access management (PAM) | BeyondTrust | Password Safe / Endpoint Privilege Management | Atlanta, GA
[5 empty] | Delinea | Secret Server / Privilege Manager | Redwood City, CA
[5 empty] | Keeper Security | KeeperPAM | Chicago, IL
[5 empty] | Microsoft | Entra Privileged Identity Management / LAPS | Redmond, WA
Governance, Risk & Compliance (GRC) Automation | Policy management, risk register, control mapping across frameworks, evidence collection, SSP/POA&M and audit workflows. | Immediate (Phase 1) | 5 | GV-05 Risk assessment & risk management GV-09 System Security Plan (SSP) & POA&M GV-07 Third-party & supply-chain risk management GV-03 Board & executive oversight GV-06 Compliance obligations & scope | ServiceNow | Integrated Risk Management (IRM) | Santa Clara, CA
[5 empty] | Archer | Archer IRM | Overland Park, KS
[5 empty] | AuditBoard | AuditBoard GRC | Cerritos, CA
[5 empty] | Vanta | Vanta Trust Management | San Francisco, CA
[5 empty] | Drata | Drata Compliance Automation | San Diego, CA
Incident Response Retainer & Forensics | Pre-negotiated emergency response, digital forensics, ransomware recovery and readiness assessments. | Immediate (Phase 1) | 3 | RS-02 Incident response testing & tabletop exercises RS-03 Regulatory & contractual incident notification RS-04 Incident analysis, forensics & containment | Mandiant (Google Cloud) | Incident Response Retainer | Reston, VA
[5 empty] | CrowdStrike | Incident Response Services | Austin, TX
[5 empty] | Palo Alto Networks | Unit 42 Retainer | Santa Clara, CA
[5 empty] | Kroll | Cyber Incident Response | New York, NY
Payment Data Security (Tokenization / P2PE / Hosted Payments) | Removes cardholder data from your environment with tokenization, PCI-validated point-to-point encryption and hosted payment pages, which reduces PCI DSS scope. | Immediate (Phase 1) | 1 | GV-21 PCI DSS scope reduction & annual validation | Stripe | Stripe Payments / Elements | South San Francisco, CA
[5 empty] | PayPal (Braintree) | Braintree Vault | San Jose, CA
[5 empty] | Fiserv | Clover / CardPointe P2PE | Milwaukee, WI
[5 empty] | Bluefin | PCI-validated P2PE | Atlanta, GA
Managed Detection & Response (24x7 SOC) | Outsourced round-the-clock monitoring, threat hunting and response for organizations without an internal 24x7 SOC. | Near-term (Phase 2) | 1 | DE-02 24x7 security monitoring & alerting (SOC / MDR) | CrowdStrike | Falcon Complete | Austin, TX
[5 empty] | Arctic Wolf | Managed Detection and Response | Eden Prairie, MN
[5 empty] | Expel | Managed Detection & Response | Herndon, VA
[5 empty] | Rapid7 | Managed Threat Complete | Boston, MA
Next-Generation Firewalls & Network Segmentation | Perimeter and internal segmentation firewalls with application awareness, IPS and deny-by-default policy. | Near-term (Phase 2) | 1 | PR-13 Network segmentation & boundary protection | Palo Alto Networks | PA-Series / VM-Series NGFW | Santa Clara, CA
[5 empty] | Fortinet | FortiGate | Sunnyvale, CA
[5 empty] | Cisco | Secure Firewall | San Jose, CA
[5 empty] | Juniper Networks (HPE) | SRX Series Firewalls | Sunnyvale, CA
Network Access Control (NAC) | Blocks unauthorized devices and enforces posture before granting network access. | Near-term (Phase 2) | 1 | PR-13 Network segmentation & boundary protection | Cisco | Identity Services Engine (ISE) | San Jose, CA
[5 empty] | HPE Aruba Networking | ClearPass | Houston, TX
[5 empty] | Forescout | Forescout Platform | San Jose, CA
Cloud Security Posture / Cloud-Native Application Protection (CSPM / CNAPP) | Continuous detection of cloud misconfigurations, excessive permissions, exposed data and workload vulnerabilities. | Near-term (Phase 2) | 2 | PR-19 Cloud security posture PR-08 Secure configuration baselines & hardening | Palo Alto Networks | Cortex Cloud (Prisma Cloud) | Santa Clara, CA
[5 empty] | CrowdStrike | Falcon Cloud Security | Austin, TX
[5 empty] | Microsoft | Defender for Cloud | Redmond, WA
[5 empty] | Wiz | Wiz Cloud | New York, NY
[5 empty] | Amazon Web Services | AWS Security Hub / GuardDuty | Seattle, WA
Asset Inventory & CMDB (Cyber Asset Attack Surface Management) | Automated, continuously reconciled inventory of hardware, software, cloud and OT assets. | Near-term (Phase 2) | 2 | ID-01 Hardware, cloud & OT asset inventory ID-02 Software inventory & authorized software | Axonius | Axonius Platform | New York, NY
[5 empty] | ServiceNow | IT Asset Management / CMDB | Santa Clara, CA
[5 empty] | Tanium | Tanium Asset | Kirkland, WA
[5 empty] | Armis | Armis Centrix | San Francisco, CA
Data Discovery, Classification & Loss Prevention | Finds and labels sensitive data (CUI, ePHI, NPI) and prevents unauthorized exfiltration across email, endpoint and cloud. | Near-term (Phase 2) | 2 | ID-03 Sensitive data inventory, classification & data flows PR-15 Data loss prevention & secure disposal | Microsoft | Purview Information Protection & DLP | Redmond, WA
[5 empty] | Varonis | Varonis Data Security Platform | New York, NY
[5 empty] | Forcepoint | Forcepoint DLP | Austin, TX
[5 empty] | Proofpoint | Enterprise DLP | Sunnyvale, CA
Third-Party Risk Management & Security Ratings | Vendor inventory, due-diligence workflows, contract tracking and continuous external security ratings. | Near-term (Phase 2) | 1 | GV-07 Third-party & supply-chain risk management | BitSight | Third-Party Risk Management | Boston, MA
[5 empty] | SecurityScorecard | Supply Chain Detection & Response | New York, NY
[5 empty] | OneTrust | Third-Party Management | Atlanta, GA
[5 empty] | ServiceNow | Third-party Risk Management | Santa Clara, CA
Immutable Backup & Cyber Recovery | Immutable, isolated backups with anomaly detection, fast orchestrated recovery and tested restore procedures. | Near-term (Phase 2) | 1 | RC-02 Business continuity & disaster recovery | Rubrik | Rubrik Security Cloud | Palo Alto, CA
[5 empty] | Cohesity | Cohesity DataProtect | San Jose, CA
[5 empty] | Commvault | Commvault Cloud | Eatontown, NJ
[5 empty] | Dell Technologies | PowerProtect Cyber Recovery | Round Rock, TX
[5 empty] | Veeam | Veeam Data Platform | Seattle, WA
[5 empty] | Nutanix | Nutanix Disaster Recovery / Data Lens | San Jose, CA
[5 empty] | Amazon Web Services | AWS Backup (with Vault Lock) | Seattle, WA
Application Security Testing & Software Supply Chain | SAST, DAST, software composition analysis, secrets scanning and SBOM generation in CI/CD. | Planned (Phase 3) | 1 | PR-17 Secure software development & application security | GitHub (Microsoft) | GitHub Advanced Security | San Francisco, CA
[5 empty] | Veracode | Veracode Application Risk Management | Burlington, MA
[5 empty] | Snyk | Snyk Platform | Boston, MA
[5 empty] | Black Duck | Black Duck SCA / Coverity | Burlington, MA
Web Application Firewall & DDoS Protection | Protects internet-facing applications and APIs from exploitation and denial-of-service attacks. | Planned (Phase 3) | 1 | PR-17 Secure software development & application security | Cloudflare | Application Security (WAF / DDoS) | San Francisco, CA
[5 empty] | Akamai | App & API Protector | Cambridge, MA
[5 empty] | F5 | Distributed Cloud WAAP | Seattle, WA
Endpoint Detection & Response (EDR / XDR) | Behavior-based detection, automated containment and forensic telemetry on endpoints and servers. | Planned (Phase 3) | 1 | RS-04 Incident analysis, forensics & containment | CrowdStrike | Falcon Insight XDR | Austin, TX
[5 empty] | Microsoft | Defender for Endpoint | Redmond, WA
[5 empty] | SentinelOne | Singularity Endpoint | Mountain View, CA
[5 empty] | Palo Alto Networks | Cortex XDR | Santa Clara, CA

## Non-compliance Risk
Risk of non-compliance (informational, not legal advice)
Framework | Legal status | Score | Penalties and enforcement | Business consequences | Official source
HIPAA Security Rule | Mandatory federal regulation | 68.1 | Tiered civil money penalties (inflation-adjusted) of up to roughly $2.1 million per violation category per calendar year; criminal penalties up to $250,000 and 10 years imprisonment (42 U.S.C. 1320d-6); multi-year corrective action plans; state attorney-general actions. | OCR investigations, settlements and multi-year corrective action plans Public listing on the HHS breach portal for breaches affecting 500+ individuals Class-action litigation and loss of patient trust | https://www.hhs.gov/hipaa/for-professionals/security/index.html
HITECH Act | Mandatory federal law (strengthens HIPAA) | 66.7 | Tiered civil money penalties up to roughly $2.1 million per violation category per year (inflation-adjusted); state attorneys general may also enforce HIPAA under HITECH. | Direct liability for business associates Public breach notification and HHS breach-portal listing State attorney-general lawsuits | https://www.hhs.gov/hipaa/for-professionals/breach-notification/index.html
PCI DSS | Contractually required for merchants and service providers that accept or process payment cards (not a U.S. government regulation) | 64.5 | Card-brand non-compliance fines passed through by the acquiring bank, higher transaction fees, liability for fraud losses and forensic investigation costs, and possible termination of card acceptance. | Fines and increased processing fees from the acquirer Liability for fraudulent charges after a breach Loss of the ability to accept payment cards | https://www.pcisecuritystandards.org/document_library/
State Data-Security Laws | Mandatory — obligations follow the residency of the individuals whose data you hold | 73.5 | State attorney-general enforcement with per-violation civil penalties (e.g., up to $5,000 per violation under the NY SHIELD Act), injunctions and multistate settlements after breaches. | Multistate attorney-general investigations after a breach Notification costs across many states Private litigation where statutes allow it | https://www.ftc.gov/business-guidance/resources/data-breach-response-guide-business
NIST CSF 2.0 | Voluntary — the de facto U.S. baseline used by regulators, insurers and courts | 65.5 | No direct penalties. Not aligning with the CSF weakens your "reasonable security" defense in FTC actions, state attorney-general actions, shareholder suits and cyber-insurance claims. | Harder to demonstrate "reasonable security" to regulators, courts and auditors Higher cyber-insurance premiums, exclusions or declined coverage Lost enterprise and government deals that require CSF alignment in security questionnaires | https://www.nist.gov/cyberframework
CISA CPGs | Voluntary — CISA's prioritized baseline for critical infrastructure | 64.3 | No direct penalties. CPGs are increasingly referenced by sector regulators and insurers; gaps materially raise ransomware and business-disruption risk. | Elevated likelihood of ransomware and business-email-compromise incidents Weaker position in sector-specific regulatory reviews Insurance underwriting challenges (MFA, backups and EDR are commonly required) | https://www.cisa.gov/cross-sector-cybersecurity-performance-goals
This assessment provides general cybersecurity compliance guidance and is not legal advice or a formal regulatory determination. Applicability should be validated with qualified legal, compliance, and cybersecurity professionals.

## Chart Data
Assessment score by framework
Category | Assessment score
CISA CPGs | 64.3
NIST CSF 2.0 | 65.5
State Data-Security Laws | 73.5
PCI DSS | 64.5
HITECH Act | 66.7
HIPAA Security Rule | 68.1
Controls by implementation status
Category | Controls
Fully Implemented | 18
Partially Implemented | 22
Not Implemented | 3
Unknown | 1
Risk distribution of open gaps
Category | Gaps
Critical | 8
High | 12
Medium | 6
Low | 0
Maturity by NIST CSF 2.0 function
Category | Score
Govern | 66.7
Identify | 63.6
Protect | 68.6
Detect | 30
Respond | 55.6
Recover | 83.3
Open gaps by category
Category | Gaps
Email & Web Security | 1
Patch Management | 1
Vulnerability Management | 1
Governance | 2
Data Protection | 2
Asset Management | 2
Monitoring & Logging | 2
Network Security | 2
Identity & Access | 2
Incident Response | 3